## Slide 2: Nominating Committee Review
ICANN66
03 November 2019 | 12:15 – 10:15
Update from the Review Implementation Working Group

## Slide 3: Presenters
Tom Barrett
Cheryl Langdon-Orr
Chair
Vice-Chair
Zahid Jamil-IG
Vice-Chair

## Slide 4: Agenda
Who Are We?
Implementation Work Phases
Detailed Implementation Plan and Recommendations
Next Steps & Community Outreach
Q&A
Q&A
1
2
3
4
5
Notes: This is a stylized agenda slide for your presentation.
To delete a box, if there are too many boxes, click the edge of the box, ensure the entire box is highlighted, then DELETE.
To update the numbers and text, click inside the circle for the numbers or in the box for the text, revise the text.

## Slide 5: Who Are We?
Agenda Item #1

## Slide 6: Mandate
ICANN Board accepted the Nominating Committee (NomCom) Review Feasibility Assessment and Initial Implementation Plan (FAIIP) from the NomCom Review Implementation Planning Team, subject to appropriate implementation costing.
14 March 2019
ICANN org to work with the NomCom Review Implementation Planning Team, who had drafted the FAIIP, to convene an implementation working group to:
draft a detailed implementation plan of the recommendations, and
oversee the implementation of the recommendations.
With its resolution, the Board has authorized the NomCom Review Implementation Working Group to make implementation-related decisions. Already, the Working Group has reached out to the community to obtain input prior to finalizing the detailed implementation.
Board Request
The NomCom RIWG submitted to the OEC the detailed implementation plan, including appropriate implementation costing.
13 September 2019
Notes: Icons or text are editable, change/add to your preference.

## Slide 7: Membership
Chart: Member Affiliation
| ALAC | RSSAC | ccNSO | GNSO/ALAC | BC | ISPCP Constituency | NCSG/NCUC | NCUC | NPOC/NCSG | RrSG | RySG | No direct affiliation
 | 11 | 1 | 4 | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 4
32 Members
No representatives from ASO, GAC, SSAC, and IPC
Held 20 teleconferences to-date
While the NomComRIWG oversees the implementation process, the group remains open to newcomers. If interested to join the NomCom Review implementation working group, please send an email to reviews@icann.org

## Slide 8: Working Group Methodology
NomCom Review mandated by ICANN’s Bylaws Article IV, Section 4.4
Transparent | meetings, documents, mailing list, action items are available via the NomComRIWG dedicated wiki
Open to any volunteer(s)
Consensus-based decision making
Fact-based analysis
Appropriate Community outreach when necessary
Implementation
Implementation Planning
Recommendations
Costing

## Slide 9: Background – NomCom2 Review Timeline
ICANN66Nov 2019
27 March 2018
5 June 2018
14 Dec 2018
14 March 2019
13 Sep 2019
Board Considers Detailed Implementation
Selection of Independent Examiner
Independent Examiner submitted Final Report published
Review Implementation Planning Team submitted Feasibility Assessment and Initial Implementation Plan (FAIIP)
Board accepted Final Report and FAIIP
Detailed Implementation Plan Submitted to Organization Effectiveness Committee (OEC)
After Nov 2019
Subject to Board approval of Detailed Implementation Plan:
Start of Implementation
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 10: Two Work Phases
Agenda Item #2

## Slide 11: Work Phases
Phase 1: Develop a Detailed Implementation Plan - COMPLETE
Detailed Implementation Plan addresses the implementation of the 27 recommendations of the NomCom Review, as specified in the IPT's Feasibility Assessment and Initial Implementation Plan and accepted by the Board.
Phase 2: Oversee the implementation of these recommendations, once approved by the ICANN Board
Expected duration 24-36 months following Board Action.
Provides realistic costings for the implementation of each of the recommendations
Approved with full consensus and submitted to the OEC on 13 September 2019.
NomComRIWG to meet weekly to oversee the implementation, in accordance with the NomCom Review Detailed Implementation Plan.
Notes: During 3Q17, the review team carefully considered the Bylaws, a limited review scope proposal, and feedback on scope received from SO/ACs.
In 4Q17, the review team agreed upon the following specific, prioritized objectives:
Evaluate the extent to which ICANN Org has implemented each prior Directory Service Review (WHOIS RT1) recommendation (16 in total) and whether implementation of each recommendation was effective
Assess the effectiveness of today’s RDS (WHOIS)
Assess the extent to which the implementation of today’s WHOIS:
  Meets legitimate need of law enforcement for swiftly accessible, accurate and complete data
  Promotes consumer trust in gTLD domain names
  Safeguards registrant data
Assess the effectiveness and transparency of ICANN enforcement of existing policy relating to WHOIS (RDS) through Contractual Compliance actions, structure and processes
Identify any portions of Bylaws Section 4.6(e), Registration Directory Service Review, which the team believes should be changed, added or removed

## Slide 12: Work Phases
13 September 2019
ICANN66Nov 2019
December
2019
ICANN67
March 2020
June
2020
Detailed Implementation Plan approved with full consensus and submitted to the OEC*
Detailed Implementation Plan is accepted by the ICANN Board
Initial outreach to ICANN community on recommendations’ implementation
Outreach Session – Updates on progress and input needed from Community
Written implementation reports provided to the OEC*
Phase 2
*OEC: Organizational Effectiveness Committee
Implementation reports on progress, include, but are not limited to, progress toward metrics and use of allocated budget.
NomCom RIWG will provide, if necessary, more details on the measurability of implementation progress including resource needs and budgetary implications. The ICANN Board, through the OEC will review those detailed plans when released.
Phase 1
December 2020
Written implementation reports provided to the OEC*
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 13: Detailed Implementation Plan and Recommendations
Agenda Item #3

## Slide 14: Detailed Implementation Plan
NomComRIWG drafted a detailed implementation plan setting out to provide for each of the twenty-seven (27) recommendations:
  a realistic timeline for the implementation,
  a definition of desired outcomes,
  an explanation of how the implementation addresses underlying issues identified in the final report,
  a way to measure current state as well as progress toward the desired outcome,
  details on the expected budgetary implications for each of the implementation steps.
Recommendations were assessed to define which are:
  Easy-to-implement and/or least costly improvements = 11
  Normal-to-implement and/or normal costly improvements = 11
  Difficult-to-implement and/or difficult costly improvements = 5

## Slide 15: Recommendations
 | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10
Outreach | X | X | X | X | X | X | X |  | X | X
NomCom Operating Procedures |  |  |  |  |  |  | X |  | X | 
Public Comment |  |  |  |  |  |  | X |  | X | X
Bylaws Change |  |  |  |  |  |  | X |  | X | X
Budget Impact |  | X | X | X |  |  |  |  |  | 
Which processes/milestones are part of these recommendations, and how will they affect ICANN community?
 | R11 | R12 | R13 | R14 | R15 | R16 | R17 | R18 | R19
Outreach |  | X | X | X |  | X | X | X | X
NomCom Operating Procedures |  | X |  | X |  | X |  |  | 
Public Comment |  |  |  |  |  |  |  |  | 
Bylaws Change |  |  |  |  |  |  |  |  | 
Budget Impact |  |  | X |  |  |  |  |  | 

## Slide 16: Recommendations
 | R20 | R21 | R22 | R23 | R24* | R25 | R26 | R27
Outreach | X | X | X | X | X | X | X | X
NomCom Operating Procedures |  |  |  |  |  |  |  | 
Public Comment |  |  |  | X | X |  |  | X
Bylaws Change |  |  |  | X | X |  |  | X
Budget Impact |  |  |  |  | X |  |  | 
R24: An empowered body of current and former NomCom members should be formed to ensure greater continuity across NomCom’s, and in particular, to recommend and assist in implementing improvements to NomCom operations.
* NomComRIWG has determined that a number of recommendations require, once implemented, the support of this ‘empowered body’ (hereafter: Standing Committee).
* NomComRIWG expects that a number of these recommendations will be implemented before the Standing Committee itself may be fully established and proposes that a sub-group of NomComRIWG members take on the tasks of the Standing Committee on an interim basis until rec. 24 is fully implemented.
Notes: The NomComRIWG has determined that a number of recommendations (2, 3, 4, 5, 6, 12, 13, 15, 18, 19, 20, 21, 22, 23, 25, 27) require, once implemented, the support of this ‘empowered body’ (hereafter: Standing Committee).

## Slide 17: Work Phase 2: Next Steps & Community Outreach
Agenda Item #4

## Slide 18: Work Phase 2: Next Steps
7 November 2019
Detailed Implementation Plan is expected to be accepted by the ICANN Board
1
2
21 November 2019
Work Phase 2 kick-off meeting
3
1 December 2019
Initiate Community outreach on recommendations’ implementation
4
7–12 March 2020 – ICANN67
Outreach Session – Updates on progress and input needed from Community
5
June 2020
Written implementation reports provided to the OEC
6
December 2020
Written implementation reports provided to the OEC
Contact mssi-secretariat@icann.org if interested in participating in our discussions.

## Slide 19: Outreach
Regular community outreach is key to the implementation of the recommendations. Within the next 6 months, following outreach for community input will potentially be carried out:
REC 1
  Compile the SO/ACs timetable for selecting their NomCom members.
  Enquire with all bodies that appoint members to the NomCom if they have a ‘job description’ for NomCom members, and also, which, if any, criteria they apply during their selection process.
  Enquire with current and former NomCom leadership what content they would like to see in a job description for future NomCom members.
REC 2/3
  Identify, in consultation with current and former NomCom and Board members, what kind of course, online/in-person etc., might meet the needs of the NomCom and also addresses the issue identified by the independent examiner.
  Work with current/former NomCom and ICANN org to identify content requirements for the training course, as well as logistical dependencies.

## Slide 20: Outreach
REC 4
  Identify, in consultation with current and former NomCom members, what kind of course, online/in-person, etc., might meet the needs of the NomCom members and addresses the issue identified by the independent examiner.
  Work with current/former NomCom members and ICANN org to identify content requirements for the training course, as well as any logistical and timing dependencies.
REC 5
  Enquire with ICANN staff and the current NomCom what the contractually defined role of the recruiting consultant(s) is and whether further steps are required.
REC 6
  Enquire with ICANN Org and the current NomCom what are the responsibilities of the evaluation consultant vis-à-vis the current job descriptions for the vacancies to be filled by the NomCom.

## Slide 21: Outreach
REC 9
  NomComRIWG to reach out to all bodies that are appointing NomCom members about planned Bylaws change, including rationale, as detailed in the Final Report
  ICANN Board directs the initiation of Bylaws change, Section 8.2., to allocate the same voting and participation rights for all NomCom members, and oversees the process.
REC 10
  NomComRIWG, in consultation with the community, to propose what principles and other factors should apply to determine the optimum NomCom’s composition, based on the current ICANN community.
REC 13
  Consult with current/former NomCom members and ICANN org to document the NomCom’s annual cycle; including (but not limited to) appointment of the leadership team, seating of the incoming members, communication with Board and other ICANN bodies about skill requirements for new appointees, recruitment outreach, interviews, selection, and announcement of incoming appointees

## Slide 22: Outreach
REC 14
  NomComRIWG to work with the current/former NomCom members, ICANN Board, ICANN org, and representatives of PTI to understand what information is currently shared between the NomCom and the bodies to which the NomCom makes appointments, including the timing of these communications.
  NomComRIWG, in coordination with the current/former NomCom members and ICANN org and the bodies that receive NomCom appointees, including the ICANN Board and PTI Board, to identify what additional information (if any) can be shared.
REC 16
  Work with the current/former NomCom members, ICANN Board and ICANN org to understand what information is currently shared between the NomCom and the bodies to which the NomCom makes appointments, including the timing of these communications.
  NomComRIWG, with support from ICANN org and in coordination with the current/former NomCom members, ICANN org and the bodies that receive NomCom appointees, including the ICANN Board, to identify what additional information (if any) can be shared.

## Slide 23: Outreach
REC 17
  Invite bodies receiving NomCom appointees, as part of the implementation of recommendations 14 and 16 to include any relevant information on desired diversity in their annual communication/advice to the NomCom.
REC 18
  Gain an overview of the current candidate communications of the NomCom by enquiring with current/former NomCom members and NomCom Staff.
  Talk to previous NomCom appointees to understand how they perceived the communication process.
REC 19
  Reach out to NomCom, ICANN org, ICANN communication team, and the recruitment consultant(s), to understand what the state of current outreach and marketing is with regard to ensuring a diverse candidate pool in response to the NomCom’s annual recruitment efforts.

## Slide 24: Outreach
REC 20
  Consult with current and past NomComs as well as ICANN org to determine what candidate attributes/data should be anonymized during the blind assessment (and when to reveal all data points)
REC 22
  Communicate with NomCom to capture and review what questions and evaluation tools are typically used by the NomCom during the deep-dive and final interview phases.
REC 23
  Consult with the wider ICANN community what additional non-confidential, non-identifiable data points should be collected and published.
REC 25
  Consult with receiving bodies to understand what (if any) performance assessment of the body itself is conducted and what skill set needs derive from that (or any other assessment) for future NomCom appointees, to avoid creating a new line of assessment or review of the receiving bodies.

## Slide 25: Outreach
REC 27
  NomComRIWG to engage with the ICANN community, ICANN Board, and ICANN org, to obtain feedback on the definition of ‘ICANN unaffiliates’, and the questions of whether being an ‘ICANN unaffiliates’ should be an additional requirement for some of the NomCom-appointed Board seats, and, if so, how many.
An outreach session will also be scheduled for ICANN67 to inform the ICANN Community on progress and receive input on some of its tasks.

## Slide 26: Q&A
Agenda Item #5

## Slide 27: Thank you!
Follow our wiki at https://community.icann.org/x/aBpIBg
Contact our working group, schedule a meeting at ICANN66: mssi-secretariat@icann.org

## Slide 28: Appendix
List of Recommendations

## Slide 29: Recommendations
# | Recommendation
R1 | Formalize a job description for NomCom members that emphasizes experience, diversity, independence, and provide that description to the SOs/ACs.
R2 | Implement and formalize training to further NomCom members’ understanding of the roles and responsibilities of Board directors and the practices of high-performing Boards at other nonprofit organizations.
R3 | Implement and formalize training for NomCom leadership to further their understanding of their roles, authority, and responsibilities, and confirm or appoint the next Chair earlier in the cycle.
R4 | Formalize training for NomCom members in the candidate evaluation process.
R5 | A professional recruiting consultant should continue to be involved in the role of identifying potential Board candidates. The role of the recruiting consultant should be clarified and published.
R6 | A professional evaluation consultant should continue to be involved in the evaluation process for Board candidates. The role of the evaluation consultant should be clarified and published.

## Slide 30: Recommendations
# | Recommendation
R7 | NomCom members, except for leadership positions, should serve two-year terms, and be limited to a maximum of two terms.
R8 | Maintain the current size of NomCom
R9 | All NomCom members should be fully participating and voting members, except for NomCom leadership.
R10 | Representation on the NomCom should be re-balanced immediately and then be reviewed every five years.
R11 | The senior staff member supporting NomCom should be accountable to and report to the office of the CEO.
R12 | NomCom leadership should have input on the NomCom budget and staffing resources.
R13 | Publish a “Process Diagram” and codify key elements of the NomCom process. Each year, the NomCom should be required to highlight and explain process changes to the ICANN community in an open session.
R14 | Formalize communication between the NomCom and the Board, SOs/ACs, and the PTI Board to understand needed competencies and experience.

## Slide 31: Recommendations
# | Recommendation
R15 | The NomCom should publish detailed job descriptions for Board, SO/AC, and PTI Board positions. The job descriptions, in combination with specific needed competencies identified each year by the NomCom, should form a basis for recruiting and evaluation efforts.
R16 | Implement and codify a system for providing feedback to the NomCom regarding the contributions and participation of members up for re-appointment by the NomCom.
R17 | Maintain current diversity requirements for NomCom appointees.
R18 | Publish a candidate communication schedule and codify a communication process with candidates.
R19 | ICANN staff and the recruiting consultant, along with NomCom members, should leverage the detailed job description and desired competencies and experience to develop a marketing plan to better target prospective candidates.
R20 | The evaluation consultant should undertake a preliminary screen of all Board candidates and provide blinded assessments to the NomCom to assist the NomCom with reducing the pool of candidates to the deep-dive shortlist.

## Slide 32: Recommendations
# | Recommendation
R21 | The NomCom should use a standardized tool to evaluate and prioritize candidates, based on desired competencies and experience as determined annually. This tool will not replace qualitative assessments of candidates.
R22 | The NomCom should provide consistent interview questions and an interviewer evaluation form for the candidates interviewed during the deep-dive phase and the final face-to-face interviews.
R23 | The NomCom should publish additional data on the candidate pool and the recruiting source of candidates.
R24 | An empowered body of current and former NomCom members should be formed to ensure greater continuity across NomCom’s, and in particular, to recommend and assist in implementing improvements to NomCom operations.
R25 | Improve NomCom selection decisions by assessing the performance and needs of all bodies receiving NomCom appointees.
R26 | ICANN should investigate advancing its nominations process into a Leadership Development function.
R27 | ICANN should investigate advancing its nominations process into a Leadership Development function.