## IDN_WG
Program | Project Code | Type | Action Item | WBS | Status | Date Assigned | Due Date | Responsible Member | Responsible Staff | Additional Notes - Action Taken | Prior Due Date | Date Completed | Date Completed Month | Date Completed Year
gTLD | IDN_WG | WP | Meeting #01 Introductions, Discuss proposed approach and timing, review background docs, homework assignments |  | Closed | 2021-05-14 | 2021-08-11 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members to send an introduction to the mailing list if they have not yet done so. |  | Closed | 2021-08-11 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Working Group to continue discussion on selection of the Vice Chair on the mailing list, noting that there are two volunteers for the role. |  | Closed | 2021-08-11 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members to complete background reading assignment if they have not yet done so. |  | Closed | 2021-08-11 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Staff to schedule next meeting for 18 August at 13:30 UTC. |  | Closed | 2021-08-11 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Staff to open doodle on possible permanent meeting slot. |  | Closed | 2021-08-11 |  | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #02 Selection of Vice Chair and background briefing from ICANN org |  | Closed | 2021-05-14 | 2021-08-18 | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #03 Background briefing from ICANN org (continued) and review of Charter Questions |  | Closed | 2021-05-14 | 2021-08-25 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members to read background documents included in Edmon’s welcome email and confirm when they have done so. |  | Closed | 2021-08-25 |  | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #04 Review of Charter Questions |  | Closed | 2021-05-14 | 2021-09-02 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members to read background documents included in Edmon’s welcome email and confirm when they have done so. |  | Closed | 2021-09-02 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members and participants to review the data and metrics part of the charter on page 19 and think about whether other data and metrics would be useful for the group to consider in deliberating on charter questions. |  | Closed | 2021-09-02 |  | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #05 Begin Review of Topic A: Consistent definition and technical utilization of RZ-LGR |  | Closed | 2021-05-14 | 2021-09-09 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | RySG and ccNSO members on the IDN EPDP to check with their Stakeholder Group to see if there are any concerns about using the RZ-LGR for existing gTLDs (charter questions a1 and a2). |  | Open | 2021-09-09 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Team to review Data and Metrics requirements in the charter and indicate whether any of the items identified are NOT necessary and/or which items are missing. |  | Closed | 2021-09-09 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | In advance of the next meeting, in preparation for further review of A3, please review the SubPro Limited Challenge / Appeal Mechanism as well as the appealing via the integration panel in the context of the RZ-LGR. |  | Closed | 2021-09-09 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members to read background documents included in Edmon’s welcome email and confirm when they have done so. |  | Closed | 2021-09-09 |  | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #06 Review of Topic A: Consistent definition and technical utilization of RZ-LGR |  | Closed | 2021-05-14 | 2021-09-16 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Leadership team to send out a “last call” for any comments/concerns about the draft project plan. Absent comments by Monday, the project plan will be submitted to Council. |  | Closed | 2021-09-16 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Keep calls at 60 minutes for now. Revisit length of meetings after the working group has deliberated on charter questions in Topic A. |  | Closed | 2021-09-16 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Staff to take back items discussed last week regarding data and metrics and see if additional nuance should be added to the bullets in the charter. |  | Closed | 2021-09-16 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members/participants to prepare to discuss charter question a3 - a10 on upcoming calls. |  | Closed | 2021-09-16 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members to read background documents included in Edmon’s welcome email and confirm when they have done so. |  | Closed | 2021-09-16 |  | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #07 Review of Topic A: Consistent definition and technical utilization of RZ-LGR |  | Closed | 2021-05-14 | 2021-09-23 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Working Group members to review the draft outreach letter to SO/AC/SG/Cs and provide any concerns/suggested edits on the mailing list no later than Tuesday 28 September at 23:59 UTC. |  | Closed | 2021-09-23 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | WG to come up with questions to be covered in the upcoming prep session on RZ-LGR. |  | Open | 2021-09-23 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Members to read background documents included in Edmon’s welcome email and confirm when they have done so. |  | Closed | 2021-09-23 |  | IDN_WG Team | Staff
gTLD | IDN_WG | MS | Release Early Input Request to SOs/ACs |  | Closed | 2021-05-14 | 2021-09-29 | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #08 Review of Topic A: Consistent definition and technical utilization of RZ-LGR |  | Closed | 2021-05-14 | 2021-09-30 | IDN_WG Team | Staff
gTLD | IDN_WG | MS | Submit Workplan to GNSO Council |  | Closed | 2021-05-14 | 2021-09-30 | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #09 ICANN Org presentation on RZ-LGR |  | Closed | 2021-05-14 | 2021-10-07 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Leadership team to follow up on the mailing list to get input on who will be able to attend the ICANN72 working session for this group. Leadership team to also seek input on the schedule of regular WG meetings around ICANN72. |  | Open | 2021-10-07 |  | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #10 ICANN Org presentation on RZ-LGR |  | Open | 2021-05-14 | 2021-10-14 | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Action Item #1: Staff to obtain response to the question “What happens in the DNS stability review and what is the relationship with the RZ-LGR?” |  | Open | 2021-10-14 |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI | Action Item #2: ALAC representatives to reach out to the leadership team with any concerns about holding a regular working session during the WG’s ICANN72 time slot. |  | Open | 2021-10-14 |  | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting #11 Topic A: Consistent definition and technical utilization of RZ-LGR |  | Open | 2021-05-14 | 2021-10-21 | IDN_WG Team | Staff
gTLD | IDN_WG | WP | Meeting - ICANN72 Seek broad community input on TPR Policy Topics |  | Open | 2021-05-14 | 2021-10-26 | IDN_WG Team | Staff
gTLD | IDN_WG | MS | Submit Monthly Project Package to Council |  | Open | 2021-05-14 |  | IDN_WG Team | Staff
gTLD | IDN_WG | MS | Submit Initial Report for Public Comment |  | Open |  |  | IDN_WG Team | Staff
gTLD | IDN_WG | AI |  |  | Open |  |  | IDN_WG Team | Staff

## closed_month
Status | Closed
Date Completed Year | Date Completed Month | Type | COUNTA of Action Item
|  | WP | 9
(blank) | (blank) | AI | 18
|  | MS | 2

## picklists
Program | Staff_Primary | Staff_Secondary | Staff | Member | Group | Role | Year | Status | Project Code | Proejct Name
RDDS | Caitlin T. | Marika K. | Emily B. | IDN_WG Team |  |  | 2020-2021 | Open | ADR | Program Planning + Action Decision Radar
RPM | Julie H. | Ariel L. | Caitlin T. |  |  |  |  | On-Hold | A_Is | GNSO Council Action Items
gTLD | Emily B. | Julie H. | Berry C. |  |  |  |  | Closed | TPR_P1 | Transfer Policy Review - Phase 1
Expiration | Caitlin T. | Ariel L. | Julie H. | [5 empty] | WPIAG | WHOIS Procedure Implementation Advisory Group
Transfers | Emily B. | Julie H. | Terri A. | [5 empty] | IDN_WG | Internationalized Domain Names
IGO | Steve C. | Mary W. | Julie B. | [5 empty] | RPM_IGO_CRWT | PDP: RPM - IGO Curative Rights Work Track
Accountability | Ariel L. | Mary W. | Staff | [5 empty] | RPM_P1 | PDP: Review of All Rights Protection Mechanisms in All gTLDs
Reviews | Steve C. | Mary W. | N.A. | [5 empty] | SubPro | PDP: New gTLD Subsequent Procedures PDP
Operations | Nathalie P. | Ariel L. | N.A. | [5 empty] | EPDP_P2 | EPDP: Temporary Specification on gTLD Registration Data - Phase 2
|  |  | N.A. | [5 empty] | IGO_CRPM | PDP: Curative Rights Protections for IGO/INGOs
|  |  | N.A. | [5 empty] | IGO_INGO2 | PDP: Protection of International Organization Names in All gTLDs
|  |  | N.A. | [5 empty] | EPDP_P1_IRT | IRT: Registration Data Policy Implementation
[9 empty] | PPSAI_IRT | IRT: Privacy & Proxy Services Accreditation Issues
[9 empty] | T&T_IRT | IRT: Translation/Transliteration of gTLD Registration Data
[9 empty] | IRP_IOT | Independent Review Process - Implementation Oversight Team
[9 empty] | CCWG_WS2 | Cross Community Working Group on Enhancing ICANN Accountability
[9 empty] | GEO | Geo Regions Review
[9 empty] | SCBO | GNSO Standing Committee on Budget and Operations
[9 empty] | SSC | GNSO Standing Selection Committee
[9 empty] | OPs | Operations General
[9 empty] | SPS_2020 | Strategic Planning Session 2020
[9 empty] | SPS_2021 | Strategic Planning Session 2021
[9 empty] | Accur_ST | Accuracy and WHOIS Accuracy Reporting System
[9 empty] | EPDP_P2A | Expedited Policy Development Process on gTLD Registration Data – Phase 2A
[9 empty] | GNSO3 | GNSO3 Review
[9 empty] | MISC | Miscellaneous