|  |  |
| --- | --- |
| **Date** | **Action / Milestone** |
| **28 Feb 2022** | Meeting #42 –   * EPDP to review recommendations as a package (pre-import into Final Report); discuss “can’t live with items” * Review Policy Impact Analysis proposed measurements |
| **28 Feb 2022** | Small team meeting on arbitral rules principles for Recs 4/5 |
| **07 Mar 2022** | Meeting #42-A –   * Emergency placeholder meeting (if required based on 28 Feb Meeting #42) |
| **07 Mar 2022** | ICANN73 Begins –   * Before and during ICANN73, EPDP representatives should be collaborating with your respective groups in preparation for the EPDP consensus call process and preparation for any minority statements. |
| **14 Mar 2022** | Meeting #43 –   * Review arbitral rules principles from small team * Overview of Final Report * Post Call - Chair’s initial consensus designation; consensus call process begins * EPDP to review Final Report and submit non-substantive edits |
| **21 Mar 2022** | Meeting #44 –   * Review non-substantive edits as required * Review and discuss issues with Chair’s consensus designations, if any |
| **28 Mar 2022** | Meeting #45 –   * Final review non-substantive edits as required * Chair’s final consensus level designations |
| **04 Apr 2022** | Meeting #46 – If required   * Minority statements due   Submit Final Report to GNSO Council |