## Slide 1: GRC

## Slide 2: Work items list: Pending work (until 75)
Completion of SoI/CoI:
  Update basic document
  Decision on introduction
  Membership consultation, Council adoption, (members adoption?)
Completion of Update of Rules:
  Timing and next steps between now
Completion of Guidelines: Council election and Board seat 11 and 12 Nomination
  Members consultation by GRC, before submitting to Council for adoption
  Council adoption

## Slide 3: Work items list post ICANN 75
Completion Board Removal, Director removal Guideline
Review and consolidation Rejection action and Approval Action Guideline
Update Rules to reflect outcome decision-making discussion DP decision-making
Confidentiality/privacy procedure
Review and update ccNSO Meeting Guideline
Review and update Roles and Responsibilties Guideline ( to be compelted by Novmeber 2022)

## Slide 4: Prioritization post ICANN75

## Slide 5: Assesment to set priorities
Importance
what is benefit for ccNSO/members,
Is it urgent?
What is effort?
What needs to be done?
What is effort ( extensive/complex <-> simple procedure)
How long will it take? (1-6 months) (6 months – 1 year)
Full GRC <-> sub-group + volunteers?

## Slide 6: Importance /Urgency assessment: work item
Important
Not Important
Not Urgent
Urgent

## Slide 7: Required effort
What needs to be done? ( extensive/complex <-> simple procedure)
How long will it take? (1-6 months) (6 months – 1 year)
Full GRC <-> sub-group + volunteers?

## Slide 8: Effort assessment: Work item
1 Year
4 weeks
Sub-Group
Full WG
Low intensity
Middle Intensity
High Intensity
Grinding

## Slide 9: Combining the assessments: Pirorities
High Impact and Urgency, low & middle intensity, start imemdiately, low hanging fruit
High impact, Grinding: Only project at a time
Not important: don’t do it, no added value
Not important, not urgent: time waster