## Sheet1
| Action Item | Secretariat |  | ICANN Staff Department Involved |  | Deadline | Current Status
|  | Focal Point | Contributor | Department | Staff member(s)
| PART A: INFORMATION ACCESSIBILITY AND DISSEMINATION |  |  |  | Item Number
1 | End-user-focussed summaries of ICANN and areas of policy work need to be developed in a standardised style | All |  | Policy, Communications | S. Pinzon, N Ashton-Hart |  | First 4 articles - IDNs, New GTLDs, WHOIS, and Domain Name Monetisation have been completed and are now available in EN, FR, ES (http://www.atlarge.icann.org/issues)
2 | Improvements to Existing Publications
2 a | Executive Summaries of all long documents from all departments should be prepared which are in clear, jargon-free language. All documents should have glossaries of ICANN-specific terms |  |  | Policy, Communications | S. Pinzon and various ICANN departments |  | This has also been identified as important to the rest of the ICANN communities - see the translation consultation results - and it is a part of the GNSO Improvements work programme. The Acronym Helper, which will be part of the new GNSO website, was seen as useful for the At-Large website.
2 b | Documents released to the public should have translated editions - if the whole text is not translated, at least the Executive Summaries should be available in the 6 UN languages |  | Dev (LACRALO), Didier (AFRALO) | Communications |  |  | DAG v3 is currently available in the six UN languages. Where translated documents related to open public comments are not available, where appropriate, efforts will be made by regional secretaries to translate texts from EN into the working languages of the regions using an on-line translation tool.
2 c | Policy-related documents should have a more standardised style of writing and structure. |  |  | Policy, Communications | S. Pinzon |  | Scott Pinzon has been hired by ICANN and is working on this amongst other duties.
3 | Secretariats to provide monthly updates on regional policy developments and other activities that will be used for the ICANN newsletter, the monthly magazine, monthly policy updates and the monthly ALAC agendas. |  | Darlene, Pavan, Dev, Dessi, Didier | Policy | S. Pinzon, N. Ashton-Hart, H. Ullrich |  | Not implemented yet. Secretariats are encouraged to submit monthly updates on the regional policy developments and activities for use in the ICANN newsletter, the policy updates and the monthly ALAC agendas. At-Large Staff will add to monthly ALAC agendas and respective regional wiki pages.
4 | More telephonic briefings to be scheduled with staff providing background on process and issues; these to be recorded for later playback | All (to provide feedback) |  | Policy | S. Pinzon, N Ashton-Hart, M. Langenegger |  | Ongoing. Plans and processes for regular telephone briefings, Podcasts and other media are being developed. Regional secretariats to provide feedback to relevant policy staff.
5 | More visibility for the At-Large community on the ICANN website. It is difficult to find a link and get to atlarge.icann.org from icann.org |  |  |  | TBC |  | Senior communications staff positions, with responsibility for the ICANN website, have been advertised.
PART B: OUTREACH AND PARTICIPATION ENHANCEMENT
6 | External Meetings Outreach
6a | Outreach to non-traditional ICANN participants is essential, and Global Partnerships should participate in more meetings where they aren't 'preaching to the converted' |  |  | Global Partnerships, Policy | M. Carver, R. Hoggarth, H. Ullrich |  | Policy staff are continuing to work with Global Partnerships staff and regional liaisons to make regional outreach more effective.
6b | Secretariats to keep staff updated about meetings in regions which should be attended by ICANN staff. (Secs to post to External Events calendar). |  | All Secretariats | Policy, Global Partnerships | M. Carver, R. Hoggarth, H. Ullrich |  | Secretariats and interested ALAC members have recently been granted access rights to the regional external events schedule and are requested to post regional events on a regular basis. Regional Secretariats are encouraged to create regional event wiki pages as a means to organize regional outreach events (eg. EURALO's wiki page: https://st.icann.org/euralo/index.cgi?euralo_regional_events).
6c | Briefings on Policy issues under consideration at ICANN should be done at regional F2F meetings, organised as part of other meetings taking place already. Some of the briefers could even be remote participants and some others F2F but at least allow two-way interaction with those in the room |  |  | Global Partnerships, Policy | M. Carver, R. Hoggarth, H. Ullrich, S Pinzon |  | Secretariats are requested to provide input into which meetings and which subjects at those meetings should be covered to At-Large staff who will work internally with other departments as required.
7 | For non-OECD countries, radio is the best means of communication about the Internet. ICANN needs to develop more radio programming about its activities and distribute them |  |  | Policy, Communications | S. Pinzon, H. Ullrich |  | S Pinzon is currently preparing a series of Podasts on current policy issues. Once the first couple of Podcasts are available the regional Secretariats are requested to send in their comments on the whether the Podcasts could be used for radio transmission.
8 | Design and development of outreach materials
8a | Brochures/leaflets for the RALOs to be combined and distributed together with the At-Large leaflet |  | All |  | S. Pinzon, N. Ashton-Hart, H. Ullrich |  | If interested, the RALO Secretariats need to contact the At-Large Staff to propose specific outreach materials.
8b | Small ICANN/At-Large conference gadgets |  | All |  | S. Pinzon, N. Ashton-Hart |  | RALO Secretariats need to contact the At-Large Staff to propose specific outreach materials.
8c | A starter pack for the new RALO members as a welcome and appreciation gesture, including basic materials, for further dissemination within the countries |  | All |  | S. Pinzon, N. Ashton-Hart, H. Ullrich |  | RALO Secretariats to work with At-Large Staff to identify the documents in the At-Large Starter Pack.
PART C: PUBLIC CONSULTATIONS ENHANCEMENT
9 | Multiple levels of input should be available, with targeted questions to allow people to contribute on particular elements of the consultation that concerned them quickly and easily, yet to not comment on other areas not of interest to them. |  |  | Policy | H. Ullrich |  | Heidi will to work with Regional Secretariats to define this issue.
10 | It is important to allow click-through on key questions to explanatory information of a balanced nature to 'draw in' commentors who needed to learn more about what they are commenting on without simply being asked to read a very long document. |  |  | Policy | H. Ullrich |  | Heidi will to work with Regional Secretariats to define this issue.
PART D: AT-LARGE COMMUNITY DEVELOPMENT
11 | Regions should be able to have differential rules about who gets to apply for travel funding if they wish |  | All (as relevant) | Policy | N. Ashton-Hart |  | ICANN would not object to such rules being established provided of course they are not arbitrary, are transparent, and do not disenfranchise ALSes unreasonably.