## Slide 1
GNSO PDP Improvements
Status Update

## Slide 2
Background
Ten proposed improvements aimed to streamline and enhance the GNSO PDP
Policy staff tasked to explore and implement next steps for each item, several in pilot format
Last status update provided in London – input received incorporated in implementation

## Slide 3
#1 Include Proposed Charter as Part of the Preliminary Issue Report
Pilot approach – first utilized as part of curative rights Preliminary Issue Report
Charter updated following public comment and submitted for GNSO Council consideration – 20 days from initiation of PDP to adoption of charter
However, too early to draw any conclusions concerning effectiveness or lack thereof
 Ensure that draft charter is submitted separately to the Council for review and specifically highlight need for input as part of the public comment forum

## Slide 4
#2 Intensity of PDP WG Meetings
It takes in general between 32 – 64 hours typically spread out over a year to a year and a half for a WG to produce its Final Report
Increasing intensity may not always be desirable / feasible, especially taking into account current workload
Pilot project for F2F facilitated PDP WG meetings approved by ICANN Board
 Facilitated PPSAI F2F WG meeting in Los Angeles. Proposal to organize session for curative rights PDP WG at ICANN 52.

## Slide 5
#3 Increase pool of PDP WG volunteers
Monthly open house newcomer WG webinars co-hosted with Council members – RSVPs have increased threefold
Implementation of PDP WG Member Onboarding Programme (see #5)
Exploring other tools to facilitate sign-up and induction

## Slide 6
#4 Require WG representative from each SG/C and SO/AC
Needs further discussion (review data to see recent make-up of WGs)
GAC-GNSO CG is exploring mechanisms for early engagement of the GAC
Implemented following London: option to join a WG as a mailing list observer – lowers the barrier for participation and ensures that a realistic assessment of active WG members can be made (new gTLD Discussion Group - +30 observers, curative rights – 4 observers)

## Slide 7
#5 Improved online tools & training
Implemented after London: calendar invites to facilitate attendance
GNSO staff to collaborate with ICANN Learn colleagues to produce ‘GNSO Learn’ videos and presentations for PDP WG Onboarding Programme
First session to focus on: ‘How is the GNSO structured?’, ‘What is consensus policy?’, ‘How does a PDP work?’

## Slide 8
#6 PDP WG Rapporteur
To be further explored post Los Angeles

## Slide 9
#7 Professional moderation / facilitation & involvement of experts
Facilitated PDP WG F2F meeting pilot
Continuation of community leadership training
Based on review of pilot, explore further options / recommendations

## Slide 10
#8 Organize workshops / discussions at the outset
To be further encouraged and promoted as issues emerge for policy consideration

## Slide 11
#9 Better data & metrics
Data metrics for policy making WG
Information / data gathering to help inform GNSO PDP Improvements effort

## Slide 12
#10 Explore flexibility in relation to public comment forum duration
Improvements to public comment forum will be launched following Los Angeles (see https://www.icann.org/news/blog/sharing-a-plan-for-public-comment-improvements)
 Council to review improvements and determine whether any further action is needed

## Slide 13
Next Steps
Review input received today
Adapt / modify approach as necessary
Continue with implementation and development of ideas / suggestions
Next update in Marrakech

## Slide 14
Questions / Comments?