AFRALO

Outreach program

Nairobi, 7-12 March 2010

(Last update: 22 December 2009)

During its Seoul general assembly, AFRALO decided to organize an outreach event in the next ICANN international public meeting in Nairobi.

This proposal gives a draft description of the event with its 2 components:

- Capacity building operation

- Exhibition

A - Capacity building

- Objective

The main objective of this project is to enhance the participation of the African end-users representatives in the Internet related policy, which is one of the main official targets of ICANN.

It was noticed that the African ALSes participation is the poorest. After an informal survey, we learned that they couldn’t assimilate the huge volume of information and activities of ICANN, and thus they feel lost. It’s because they didn’t get the basic knowledge regarding the ICANN structure, mission and activities. If we don’t give them simplified and popularized elements of knowledge regarding organizational structure, communication and policy making, they will still feel lost and stay inactive and marginalized.

During the 6 days of the ICANN meeting in Nairobi, the project aims at providing representatives of AFRALO ALSes with briefings on the key policies, issues, activities and structure of ICANN. These briefings will be conducted by relevant ICANN officers and staff, and allow for open discussion.

- Organization of the sessions

For the best efficiency, the sessions will be organized from Monday to Friday early in the morning (From 7 to 9 a.m.) to allow the AFRALO ALS representatives to participate in ICANN meetings in order to apply what they learned during the morning sessions. A session of one full day (Sunday) will be dedicated to the overall presentation of ICANN structure and mission, when the morning sessions of the 5 remaining days will be used to detail each ICANN constituency mission and activities.

This organization would allow the use of the At-Large meeting room since it’s equipped with the interpretation facilities. The only constraint will be that All At-Large meetings will only be able to start at 9:30 a.m..

- Attendees

|  | ALS Name |  | Contact Person. | Country |
| --- | --- | --- | --- | --- |
| 1 | 131 | Ofok Al-Tanmia | Shaarawy Abdel Baky | Egypte |
| 2 | 123 | Consortium d'Appui aux Actions pour la Promotion et le Développement de l'Afrique (CAPDA) | Michel TCHONANG LINZE | Cameroon |
| 3 | 121 | Bokk Jang Bokk Jef Senegal | Fatimata Seye Sylla | Senegal |
| 4 | 117 | Fédération Méditerranéenne des Associations d'Internet | Tijani BEN JEMAA | Tunisia |
| 5 | 111 | Moroccan Association of Civil Society for Information Society (MACIS) | Belid NAOUAR | Morocco |
| 6 | 104 | SchoolNet Africa | Amr Hamdy | Egypte |
| 7 | 100 | ACOULL (Association Congolaise des Utilisateurs de Logiciels Libres) | Gabriel BOMBAMBO | RDC |
| 8 | 97 | ISOC BURUNDI | Victor Ciza | Burundi |
| 9 | 94 | ISOC-BENIN | Yaovi Atohoun | Benin |
| 10 | 93 | CENTRE DE PROMOTION ET DE VULGARISATION DE L'INFORMATIQUE | Arnold MULENDA YAMUKANDU | RDC |
| 11 | 85 | CENTRE AFRICAIN D’ECHANGE CULTUREL | Baudouin Schombe | RDC |
| 12 | 84 | ISOC-Mali (Internet Society, Mali chapter) | Hawa Diakite | Mali |
| 13 | 75 | Tunisian Internet Society | Khaled Koubaa | Tunisia |
| 14 | 37 | The South African Chapter of the Internet Society | Alan Levin | South Africa |
| 15 | 29 | Nigerian Internet Users Coalition | Adetokunbo Abiola | Nigeria |
| 16 | 24 | African Youth Foundation | Paulyn Jansen | Ghana |
| 17 | 18 | ISOC-DRC | Didier Rukeratabaro Kasole | RDC |
| 18 | 11 | Moroccan Internet Society (MISOC) | Abdelaziz Helali | Morocco |
| 19 | 7 | Anais.AC | Robertine Tankeu Keutchankeu | Cameroon |
| 20 | 3 | Sudan Internet Society | Mohamed Albesheer | Sudan |

To achieve its objective, this operation has to be followed by all the AFRALO ALS representatives. The best is to have 2 representatives per ALS. But if we don’t manage to find the necessary financing resources, we can run it with at least one person per ALS:

  - Option 1: 20 Persons representing the 20 AFRALO ALSes (1 per ALS)

  - Option 2: 40 persons representing the 20 ALSes (2 per ALS)

- Means required

  - Travel support

    - Option 1 (1 per ALS)

Among the 20 persons to attend the capacity building, 5 will not need travel support since they are funded by ALAC and NomCom. The list of the selected persons for the Nairobi fellowship program published on 18 December contained none of the AFRALO ALS representatives. Thus, 15 persons will need to be funded.

The global cost of the travel support would be around 48,225 US$ based on 1,500 $ for the air fare, 150 $ per night for the accommodation, and 95 $ per day for the per diem.

    - Option 2 (2 per ALS)

35 persons to be funded (40-5)

The global cost of the travel support would be around 112,525 US$

  - Logistical aspects

    - A room for 25 persons (option 1) or 45 persons (option 2), equipped with the simultaneous interpretation infrastructure.

    - Tow translators (English and French)

- Coordination

This operation needs the contribution of At-Large secretariat and Global Partnerships staff.

It also requires a dedicated coordinator who will work with the ICANN Meetings staff to coordinate all the logistical aspects, including arranging the various trainers. Perhaps Gisella Gruber White, who has African roots, and who is perfectly bilingual would be a good choice.

- Optimization

The format proposed is similar to that of the Global Partnerships fellowships program, and shares similar aims. Collaboration with the Fellowship program staff will be suitable.

If an agreement is achieved, we can optimize the cost of the whole program by merging the AFRALO ALS representatives with the Fellows for most of the daily sessions, using the same room and the same facilities. Some AFRALO specific sessions will be split, making use of the At-Large meeting facilities.

B - Exhibition