Draft Translation and Transliteration of Contact Information PDP WG Work Plan & Timeline (updated 23 March 2015)

| Target Date | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 19 December 2013 | T&T Meeting | - Inaugural Meeting | All |
| 09 January 2014 | T&T WG Meeting | - Confirmation of Co-Chairs - Overview discussion of relevant Charter questions | All |
| 16 January | T&T WG Meeting | - Assess Work Plan & WG approach - Discuss SG/C Input Template & SO / AC outreach message | All |
| 23 January | T&T WG Meeting | - Finalise Work Plan & WG Approach - Finalise SG/C Input Template & SO/AC outreach | All |
| 24 January | Send out SC/C Input Template & SO/AC outreach |  | Staff |
| 30 January | T&T WG Meeting | - Review Charter Questions | All |
| 6 February | T&T WG Meeting | - Review Charter Questions | All |
| 13 February | T&T WG Meeting | - Review Charter Questions | All |
| 20 February | T&T WG Meeting | - Review Charter Questions | All |
| 21 February | Deadline for SG/C and SO/AC outreach | - Distribute SO/AC and SG/G Input Review Tool | Staff |
| 27 February | T&T WG Meeting | - Review Charter Questions in light of SG/C/SO/AC comments | All |
| 6 March | T&T WG Meeting | - Review Charter Questions in light of SG/C/SO/AC comments | All |
| 13 March | T&T WG Meeting | - Review Charter Questions in light of SG/C/SO/AC comments - Planning for F2F in Singapore | All |
| 26 March | F2F T&T WG Meeting, Singapore | - Presentation of work accomplished so far - Continue to review SG/C/SO/AC comments | All |
| 3 April | T&T WG Meeting | - Review of F2F Meeting - Continue review of SG/C/SO/AC comments | All |
| 10 April | T&T WG Meeting | - Finalizing review of SG/C/SO/AC comments | All |
| 17 April | T&T WG Meeting | - Finalizing review of SG/C/SO/AC comments | All |
| 24 April | T&T WG Meeting | - Stock Take: Where are we, what are the key issues that needs discussion - Review of relevant work that is taking place in other relevant efforts | All |
| 01 May | T&T WG Meeting | - Review of Work Plan | All |
| 08 May | T&T WG Meeting | - Discussion on open issues & development of draft recommendations | All |
| 15 May | T&T WG Meeting | - Discussion on open issues & development of draft recommendations | All |
| 22 May | T&T WG Meeting | - Discussion on open issues & development of draft recommendations | All |
| 29 May | T&T WG Meeting | - Discussion on open issues & development of draft recommendations | All |
| 05 June | T&T WG Meeting | - Discussion on open issues & development of draft recommendations | All |
| 12 June | T&T WG Meeting | - Preparation for London F2F Meeting | All |
| 25 June | F2F WG Meeting, London | - Presentation of Work achieved so far - Discussion on open issues & development of draft recommendations | All |
| 3 July | T&T WG Meeting | - Discussion on open issues & development of draft recommendations | All |
| 10 July | T&T WG Meeting | - Discussion on open issues & development of draft recommendations | All |
| 17 July | T&T WG Meeting | - Continue review of comments received | All |
| 24 July | T&T WG Meeting | - Continue review of comments received | All |
| 31 July | T&T WG Meeting | - Continue review of comments received | All |
| 7 August | T&T WG Meeting | - Continue review of comments received | All |
| 14 August | T&T WG Meeting | - Continue review of comments received | All |
| 21 August | T&T WG Meeting | - Continue review of comments received | All |
| 28 August | T&T WG Meeting | - Continue deliberations on open issues identified in the Initial Report - Schedule / Work plan check point | All |
| 4 September | T&T WG Meeting | - Continue deliberations on open issues identified in the Initial Report | All |
| 25 September | T&T WG Meeting | - Preparation for Los Angeles F2F Meeting | All |
| 02 October | T&T WG Meeting | - Preparation for Los Angeles F2F Meeting | All |
| 15 October | F2F WG Meeting, Los Angeles | - Discussion of draft initial report | All |
| 30 October | T&T WG Meeting | - Review Work Plan | All |
| 06 November | T&T WG Meeting | - Discussion of Draft Initial Report | All |
| 13 November | T&T WG Meeting | - Discussion of Draft Initial Report | All |
| 20 November | T&T WG Meeting | - Prepare Initial Report | All/Staff |
| 27 November | T&T WG Meeting | - Prepare Initial Report | All/Staff |
| 04 December | T&T WG Meeting | - Prepare Initial Report | All/Staff |
| 11 December | T&T WG Meeting | - Prepare Initial Report | All/Staff |
| 15 December | Submit Initial Report |  | Staff |
| 16 December | Open Public Comment |  | Staff |
| 18 December | No meeting |  |  |
| 25 December | No meeting |  |  |
| 1 January | No meeting |  |  |
| 8 January | No meeting |  |  |
| 15 January | T&T WG Meeting | - General discussion | All |
| 22 January | T&T WG Meeting | - General discussion | All |
| 29 January | T&T WG Meeting | - General discussion | All |
| 1 February 2015 | Closing of Public comment |  | Staff |
| 12 February | T&T WG Face-to-Face Meeting | - Review of achievements / start comment review | All |
| 19 February | No Meeting post ICANN52 |  |  |
| 26 February | T&T WG Meeting | - Review face-to-face meetings and discuss any new issues that may have come up | Staff/All |
| 5 March | T&T WG Meeting | - Review public comments | All |
| 12 March | T&T WG Meeting | - Review public comments | All |
| 19 March | T&T WG Meeting | - Review public comments | All |
| 02 April | T&T WG Meeting | - Status update – plan head | All |
| 07 April | Circulate Draft Final Report | - Discuss Final Report | Staff |
| 09 April | T&T WG Meeting | - Discuss Final Report | All |
| 16 April | T&T WG Meeting | - Discuss Final Report | All |
| 23 April | T&T WG Meeting | - Discuss Final Report | All |
| 30 April | T&T WG Meeting | - Discuss Final Report | All |
| 07 May | T&T WG Meeting | - Discuss Final Report | All |
| 11 May | Submit Final Report | - Deadline for submission to be considered during May GNSO Council Meeting | Chairs |
| 14 May | T&T WG Meeting | - Discuss Final Report (if May deadline is missed) | All |
| 21 May | T&T WG Meeting | - Discuss Final Report (if May deadline is missed) | All |
| 28 May | T&T WG Meeting | - Discuss Final Report (if May deadline is missed) | All |
| 04 June | T&T WG Meeting | - Discuss Final Report (if May deadline is missed) | All |
| 11 June | T&T WG Meeting | - Discuss Final Report (if May deadline is missed) | All |
| 14 June | Submit Final Report | - Deadline for submission to be considered during June GNSO Council Meeting in Buenos Aires | Chairs |