## Slide 1
FY17 Planning process
Xavier Calvez | Meeting with CWG DT-O team | 4 November 2015

## Slide 2: FY17 Planning: Critical path with Transition
1 Dec 2015
15 Jan
2016
5 Mar
2016
Jun
2016
Departmental budgeting
Production
Final Draft
Public comment on final draft
To Summarize:
We will keep the process on time, and will keep assumptions simple.
ICANN Management will finalize assumptions on Transition/PTI by 15 January 2016.
Board Approval
30 Apr
2016
Delivery to ICANN Board/NTIA in Dec 2015
Phase 2
Phase 3
Phase 1
FY17 Planning process
Transition process

## Slide 3: FY17 Planning: pragmatic approach
Feedback from Planning working group (Dublin – Sunday 18th):
“Keep things simple”
  To let all understand easily the OP&B (Staff/Board/Stakeholders/Public)
  To be efficient in producing the OP&B
“Keep the process on time”
    For accountability, critical now
    Best practice + efficiency

## Slide 4: FY17 Planning: Suggested option
BASE scenario into the OP&B (fully described) + High level description of alternative scenarios,
BASE scenario: PTI is implemented, no change to operational separation of the IANA functions (specific staff/processes + shared infrastructure/overheads)
Open questions, requiring assumptions:
  When can implementation start?
  How long will implementation take?
  Advantage of BASE approach (i.e. “no change to operational separation”) limits impact of timing for planning purposes.