## Slide 1
Rodrigo Saucedo | Webinar | 30 March 2015
LAC Strategy update

## Slide 2: Agenda
LAC Strategic Plan overview
  LAC Strategy timeline
  Overall implementation
  Implementation Period August 14 - August 15
  LAC Community participation
  Communicating the LAC Strategy
Projects with LACRALO
How to get involved
Q&A
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 3
LAC Strategic Plan overview
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 4: LAC Strategy Timeline
April
2013
May
2014
June
2014
March
2015
June
2015
Community presented LAC Strategic Plan in Beijing
5 pilot projects implemented
The Implementation Plan for the rest of the projects was presented
Implementing the projects on the first period – August 2014 to August 2015
We will start implementing the projects of the second period.
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 5: Overall implementation
Chart: 
| Initial Projects | First Period August 14 - August 15 | Second Period June 15 - June 16
LAC Strategy Projects | 15 | 37 | 23
Column1
75 projects in total
Notes: To create a quick pie charts, click the slice of pie inside the circle, grab one of the ends and adjust the size of the slice to your desired length.
The % numbers do not automatically adjust but you can manually edit the % number in the text box.

## Slide 6: Implementation on Period August 14 - August 15
Chart: 
| Started | Not started
First Period August 14 - August 15 | 19 | 18
Notes: To create a quick pie charts, click the slice of pie inside the circle, grab one of the ends and adjust the size of the slice to your desired length.
The % numbers do not automatically adjust but you can manually edit the % number in the text box.

## Slide 7: LAC Community participation
1
Number of Latin America and Caribbean Community members participating in one or more projects of the LAC Strategic Plan
Latin America/
Caribbean Islands
Latin America
Caribbean
31 people
Steering Committee (16 members)
9 members of this Committee are involved in 1 or more projects.
14 people

## Slide 8: List of community members
Latin America | Caribbean
Olga Cavalli | Carlton Samuels
Carolina Aguerre | Michelle Marius
Vanda Scartezini | Cintra Sooknana
Alberto Soto | Rodney Taylor
Ruth Puente | Bennette Thomas
Gabriela Szlak, | Christopher Herbert,
Antonhy Harris | Michelle Marius
Eduardo Santoyo | Christopher Herber
Humberto Carrasco | Michelle Marius
Esteban Lescano | Claire Craig
Christian O´Flagherty, | Collin Bacchus
Ariel Grazer | Rayman Khan
Carlos Aguirre | Shiva Sissesar
Renata Aquino | Dev Anand Teelucksingh
Maritza Aguero | 
Hugo Salgado | 
Juan Manuel Rojas | 
Alejandro Acosta | 
Antonio Alberti | 
Victor Hugo Fernandes | 
Alyne Andrade | 
Lacier Dias | 
Juan Jung | 
Alejandra Reynoso | 
Sofia Zerbino | 
Alicia Paz | 
Daniel Oppermamn | 
Bruno Closs | 
Gonzalo Romero | 
Vanda Scartezini | 
Celia Lerman | 

## Slide 9: LAC Strategy Communication
Newsletter
Regional Website
Social media
Monthly Webinar

## Slide 10
Projects
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 11: Capacity Building - Webinars
2.7.2 Working with the LACRALO community to create a syllabus for webinars for the entire year focused on training members of this community and end-users over all.
Working Group:
Alberto Soto
Humberto Carrasco
Carlos Aguirre
ICANN Support Staff – At Large and LAC GSE
https://community.icann.org/pages/viewpage.action?pageId=52892572

## Slide 12: Capacity Building - E-learning Courses
2.7.3 Working with the LACRALO community to complement the content they already have for e-learning with focus on training members of this community and end-users over all.
Working Group:
Alberto Soto
Humberto Carrasco
Carlos Aguirre
ICANN Support Staff – At Large and LAC GSE
Avoid Double effort
Introduction to LACRALO – ICANN Learn
Improve what already exist

## Slide 13: Outreach
2.7.1 To create surveys, contests and rewards to Internet users from the region to determine the level of knowledge of ICANN related matters.
Working Group:
Alberto Soto
Maritza Aguero
Trivia Contest
Facebook Application
Price/award

## Slide 14: Outreach
2.1.4 Supporting outreach events in the region related to ICANN, GSE will allocate the budget for two additional trips to the CROPP program.
Working Group:
Dev Anand
Alberto Soto
GSE Budget will allocate an extra trip to the CROPP Program
Added Value:
An outreach calendar
Help avoid not using this CROPP trips
Try to balance between Caribbean and LA

## Slide 15
How to get involved
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 16: How to get involved
LAC Strategic Plan
https://community.icann.org/pages/viewpage.action?pageId=48348889
Implementation Plan
https://community.icann.org/pages/viewpage.action?pageId=49357942
ICANN’s LAC staff
Rodrigo de la Parra – rodrigo.delaparra@icann.org
Albert Daniels – albert.daniels@icann.org
Daniel Fink - daniel.fink@icann.org
Rodrigo Saucedo rodrigo.saucedo@icann.org

## Slide 17
Email: rodrigo.saucedo@icann.org
Thank You
Notes: You can adjust the email/web address to whichever email or web address is best suited to your presentation. This should be your final slide.