## Slide 1
At-Large Review Briefing
1 May 2015

## Slide 2: Roles and Responsibilities
SIC
Oversight
Accept Report*
Staff
Prepare RFP
Independent Examiner
Review of documents, records
Develop and conduct 360 Assessment
Review Working Party**
Coordinate 360 Assessment
Coordinate Interviews
Approve Plans*
Run Examiner Selection
Monitor Process
Prepare Review Implementation Plan
Manage Report Process
Conduct interviews
Prepare report
Engage with stakeholders for clarification and correction
Support Examination
Provide clarification and corrections
Prepare Review Implementation Plan
Conduct Self-Assessment
Support outreach and engagement
Observe proceedings
Collect evidence
Address key considerations for data collection and review methodology
Assist with outreach and engagement
*Prepare Recommendations for Board Action
** Formed by Organization under Review

## Slide 3: Proposed Timeline
Jan-April
2015
May-Oct 2015
Nov ‘15-Apr ‘16
Apr ’16-Jan ‘17
Jan ‘17-Jan ‘18
Next
Steps
Plan for At-Large Review
Conduct Self-Assessment
Conduct Competitive Bidding
Conduct Review
Plan Implementation and implement improvements
The At-Large Review Working Party will be engaged from May 2015 through January 2017.
The At-Large Review Preparatory Questions are posted on the wiki.
The independent examiner will be appointed during the Spring of 2016.
Planning for implementation will start January 2017 and end July 2017; implementation improvements will start upon completion of the planning phase and will end in January 2018.
To Summarize

## Slide 4
Discussion and Q&A

## Slide 5
Thank You