## Slide 1
Transition Implementation
Status Reporting
21 January 2016

## Slide 2
CWG Status Update

## Slide 3: RZMS, RZMA & Names SLEs
VRSGN’s
RZMS code changes (parallel testing)
ICANN’s
RZMS code changes (parallel testing)
ICANN’s RZMS code changes (RZA)
RZMA ready for public review
Key Dates:
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
ICANN’s RZMS code changes (SLEs)
SLA targets defined
SLA dashboard ready
Start
parallel testing
Remove RZA Role in production RZMS
 | Project | Description | Plan Completion Date | Status | % Complete
 | RZMS changes to remove RZA role and support parallel testing | Remove NTIA's authorization process from RZMS (code changes for ICANN and Verisign), and parallel testing. | 09/30/16 |  | 
 | Names SLEs (SLEs for Naming Community) | RZMS code changes to accommodate new SLEs, inclusion of performance targets in ICANN-PTI contract, dashboard reporting of SLAs. | 09/30/16 |  | 
 | RZMA (Agreement with Root Zone Maintainer) | Completion of draft RZMA. | 01/31/16 |  | 
10%
01/18/16
Status As Of Date:
10%
Project Updates: Preliminary draft of report on existing data parsing received and under review. Additional time may be needed to complete draft RZMA | Upcoming Activities: Continue discussions with Verisign to complete draft RZMA Continue to work on RZMS code changes for SLEs Publication of report on existing data parsing | Open Items:
On-track
At risk, but recovery still possible
Target will be missed
Not started
60%
Insert SLAs into ICANN-PTI contract
* All dates are estimates
DRAFT for Discussion
Existing data parsing conclusions shared

## Slide 4: PTI
 | Project | Description | Plan Completion Date | Status | % Complete
 | PTI (Post-Transition IANA) | Formation of PTI entity. | 09/30/16 |  | 
10%
Updates: Continue drafting of PTI implementation plan | Upcoming activities: | Open Items:
01/18/16
Status As Of Date:
DRAFT for Discussion
* All dates are estimates
On-track
At risk, but recovery still possible
Target will be missed
Not started
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
PTI entity legally
formed
ICANN-PTI contract ready for public review
PTI budget adopted by ICANN Board
501c3 status ready

## Slide 5: IPR, RZERC, CSC & Escalation Processes
 | Project | Description | Plan Completion Date | Status | % Complete
 | IANA IPR | Transfer of IANA IPR to a neutral trust. |  |  | 
 | RZERC (Root Zone Evolution Review Committee) | Formation of committee to advise ICANN Board on RZMS architectural and operational changes. | 09/30/16 |  | 
 | CSC (Customer Service Standing Committee) | Formation of committee to monitor PTI performance. | 09/30/16 |  | 
 | Escalation Processes | Updating of existing IANA operational complaint and escalation processes. | 09/30/16 |  | 
01/18/16
Status As Of Date:
0%
0%
0%
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
Draft charter ready
CSC constituted
0%
Project Update: | Upcoming Activities: | Open Items:
DRAFT for Discussion
* All dates are estimates
On-track
At risk, but recovery still possible
Target will be missed
Not started

## Slide 6: Enhancing ICANN’s Accountability
 | Project | Description | Plan Completion Date | Status | % Complete
 | ICANN’s Bylaws | Updating of ICANN Bylaws. | 09/30/16 |  | 
 | IRP Enhancements | Implement enhancements to Independent Review Process. | 09/30/16 |  | 
 | RR Enhancements | Implement enhancements to ICANN's reconsideration request process. | 09/30/16 |  | 
 | Empowered Community Enhancements | Implement processes and mechanisms in support of the empowered community. | 09/30/16 |  | 
10%
Project Update: | Upcoming Activities: | Open Items: Final language of CCWG proposal
01/18/16
Status As Of Date:
0%
0%
0%
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
Bylaws posted for public comments
ICANN Board adopts Bylaws
* Key dates are based on assumption of proposals being delivered in January 2016
DRAFT for Discussion
* All dates are estimates
On-track
At risk, but recovery still possible
Target will be missed
Not started

## Slide 7
Appendix 1
High-Level Projects Plans

## Slide 8: RZMS Changes & Names SLEs
RZMS & parallel testing activities
Parsing of existing data activities
SLE activities
ICANN-PTI contract activity
DRAFT for Discussion
2015
ICANN determines feasibility of existing data use
ICANN parses existing data (per feasibility determination)
ICANN collects & operationalizes SLE metrics
CWG reviews SLE metrics & defines SLAs
ICANN makes RZMS code changes for SLEs
ICANN inserts SLAs into ICANN-PTI contract
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
IANA Contract Expires
ICANN develops SLAs dashboard
ICANN makes RZMS code changes to remove RZA role
Parallel testing
Verisign makes code changes to support parallel testing
ICANN makes RZMS code changes to support parallel testing
Project Updates:
Preliminary draft of report on existing data parsing received and under review.
Open Items:
Upcoming Activities:
Continue to work on RZMS code changes for SLEs
Publication of report on existing data parsing
✔
Baseline
Current Plan
Status: On-track
% Complete:
10%
Status As Of: 01/18/16
* Timeframes are estimates
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 9: IANA IPR
Baseline
Current Plan
[insert] activities
[insert] activities
[Insert] activities
DRAFT for Discussion
2015
Task 1
Task 2
Task 3
Task 4
Task 5
Task 3
Task 6
Task 7
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
Expiration of IANA Contract
Task 8
Project Updates:
Open Items:
Upcoming Activities:
Status: No Started
% Complete:
0%
Status As Of: 01/18/16
* Timeframes are estimates
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 10: RZERC (Root Zone Evolution Review Committee)
Baseline
Current Plan
Implementation plan activity
RZERC activities
USG activity
DRAFT for Discussion
2015
Define implementation plan
ICANN drafts charter to ICG’s specifications
CWG reviews draft charter & ICANN updates
ICANN constitutes RZERC
USG approves proposals
ICANN puts in place secretariat support
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
Expiration of IANA Contract
ICANN coordinates with NTIA on any ongoing architectural & operational changes
ICANN Board adopts RZERC charter
Project Updates:
Open Items:
Upcoming Activities:
Draft implementation plan
Status: No Started
% Complete:
0%
Status As Of: 01/18/16
* Timeframes are estimates
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 11: Customer Standing Committee (CSC)
Baseline
Current Plan
Implementation plan activity
CSC activities
USG activity
DRAFT for Discussion
2015
Define Implementation Plan
ICANN constitutes CSC
USG approves proposals
ICANN confirms reporting needs with CSC
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
Expiration of IANA Contract
ICANN puts in place secretariat support
Project Updates:
Open Items:
Upcoming Activities:
Draft implementation plan
Status: No Started
% Complete:
0%
Status As Of: 01/18/16
* Timeframes are estimates
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 12: IANA Operational Escalation Processes
Baseline
Current Plan
Implementation plan activity
Escalation mechanisms activities
DRAFT for Discussion
2015
Define Implementation Plan
Revise process documentations
Define mediation process for Names community’s IANA Customer Service Complaint Resolution Process
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
Expiration of IANA Contract
Project Updates:
Open Items:
Upcoming Activities:
Status: No Started
% Complete:
0%
Status As Of: 01/18/16
* Timeframes are estimates
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 13: Post-Transition IANA (PTI) – 1 of 2
* Timeframes are estimates
Implementation plan activity
PTI activities
USG activity
DRAFT for Discussion
2015
Define implementation plan
ICANN prepares and files 501c3 paperwork
ICANN incorporates affiliate
ICANN-PTI contract drafted & reviewed
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
Expiration of IANA Contract
USG approves proposals
ICANN posts draft contract for public review
ICANN constitutes PTI Board
ICANN incorporates SLEs1
ICANN executes contract
Contract becomes effective
Updates:
Began drafting implementation plan
Open Items:
1 Dependent on performance targets being defined by end of August 2016 under Names SLEs project
Status: On-track
Upcoming Activities:
Continue drafting implementation plan
Baseline
Current Plan
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 14: Post-Transition IANA (PTI) – 2 of 2
* Timeframes are estimates
DRAFT for Discussion
2015
ICANN validates budgeting assumptions with CWG
Public comment period on PTI budget
ICANN drafts PTI budget
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
Expiration of IANA Contract
ICANN Board approval of PTI budget
Status: On-track
Project Update:
Plan reflects PIT budget development process as part of ICANN FY17 OP&B process and timeline
Open Items:
Upcoming Activities:
Implementation plan activity
PTI activities
USG activity
Baseline
Current Plan
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 15: ICANN Bylaws (assumes proposals delivered in January 2016)
Final proposals delivered to ICANN Board
Prep proposed amendments to ICANN’s Bylaws
ICANN Board takes action to post Bylaws for comments
Finalize Bylaws
ICANN Board adopts & transmits Bylaws to NTIA
Public comment period
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
Expiration of IANA Contract
Project Updates:
Open Items:
Final language from CCWG proposal
Upcoming Activities:
DRAFT for Discussion
Status: On-track
% Complete:
10%
Status As Of: 01/18/16
* Timeframes are estimates
Bylaws activity
USG activity
Baseline
Current Plan
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 16
Appendix 2
RIRs and IETF Status Updates

## Slide 17: RIRs SLAs & IETF MoU Supplemental Agreement
 | Project | Description | Plan Completion Date* | Status | % Complete
 | RIRs SLAs | Completion of draft agreement, including SLAs with RIRs, and operationalization of SLAs. | 06/30/16 |  | 
 | IETF MoU Supplemental Agreement | Completion of draft ICANN-IETF MoU Supplemental Agreement. | 06/30/16 |  | 
01/18/16
Status As Of Date:
75%
50%
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
IETF MoU Suppl. Doc finalized
RiRs SLAs Document
finalized
Tools/ processes updated
Updates: Call with RIRs to discuss remaining items scheduled. | Upcoming activities: | Open Items:
DRAFT for Discussion
* Completion Date dependent on USG’s approval of proposals
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started

## Slide 18: RIRs SLAs
Baseline
Current Plan
DRAFT for Discussion
2015
Finalize SLA document with RIRs
Update tools/processes to accommodate SLAs
SLA document becomes effective
Execute SLA document
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
IANA Contract Expires
IANA contract expires
Project Updates:
Call with RIRs to discuss remaining items scheduled
Open Items:
Upcoming Activities:
Continue engagement with the RIRs to finalize document
USG approves proposals
RIRs SLAs activities
USG activity
Status: On-track
% Complete:
50%
Status As Of: 01/18/16
* Timeframes are estimates
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 19: IETF MoU Supplemental Agreement (“MoU”)
Baseline
Current Plan
MoU activities
USG activity
DRAFT for Discussion
2015
Finalize MoU document
Update tools/processes to accommodate SLAs
MoU document becomes effective
Execute MoU document
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
22
Final Proposals
To ICANN Board
5
ICANN 55
TBD
USG approves proposals
27
ICANN 56
30
IANA Contract Expires
IANA contract expires
Project Updates:
Open Items:
Upcoming Activities:
USG approves proposals
Status: On-track
% Complete:
50%
Status As Of: 01/18/16
* Timeframes are estimates
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 20
Appendix 3
Post Transition Projects

## Slide 21: Post Transition Projects
 | Project | Description
 | IANA Remedial Action Procedures | New remediation process for the CSC to address poor performance with IANA before escalation to the ccNSO/GNSO. To be finalized between CSC and IANA post transition. (CWG)
 | IANA Function Review (IFR) | Review of PTI’s performance against the ICANN-PTI contract and SOW. First IFR to take place 2 years after transition. (CWG)
 | Special IFR | To be initiated when CSC remedial action procedures and IANA problem resolution process are followed and failed to correct deficiency. (CWG)
 | Separation Cross Community Working Group (SCWG) | To be formed if the special IFR results in a recommendation for separation. (CWG)
 | Transition to Successor IFO | Plan for Transition to Successor IFO. (CWG)
 | Formal study on changes to root zone content | To investigate whether there is need to increase the robustness of the operational arrangements for making changes to the root zone content to reduce or eliminate single point of failure. (CWG)
 | CCWG-Accountability Work Stream 2 | To commence at ICANN55 and complete by end of 2016; WS 2 elements include: Diversity, SO/AC accountability, Transparency, Human Rights, Jurisdiction, Interim Bylaw. (CCWG)
−
−
−
−
−
−
−