## Slide 1
Transition Implementation
Status Reporting
02 June 2016

## Slide 2: RZMS, RZMA & Names SLEs
VRSGN’s
RZMS code changes (parallel testing)
ICANN’s
RZMS code changes (parallel testing)
ICANN’s RZMS code changes (RZA)
RZMA ready for public review
Key Dates:
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
ICANN’s RZMS code changes (SLEs)
SLA targets defined
SLA dashboard ready
Start
parallel testing
Remove RZA Role in production RZMS
 | Project | Description | Plan Completion Date | Status | % Complete
 | RZMS changes to remove RZA role and support parallel testing | Remove NTIA's authorization process from RZMS (code changes for ICANN and Verisign, and parallel testing). | 09/30/16 08/15/16 07/06/16 |  | 
 | Names SLEs (SLEs for Naming Community) | RZMS code changes to accommodate new SLEs, inclusion of performance targets in ICANN-PTI contract, dashboard reporting of SLAs. | 09/30/16 08/15/16 |  | 
 | RZMA (Agreement with Root Zone Maintainer) | Completion of draft RZMA. | 01/31/16 / 02/29/16 04/15/16 / 04/30/16 05/15/16 / 05/31/16 |  | 
80%
05/27/16
Status As Of Date:
60%
Project Updates: Completed 55 days of 90-day Parallel Testing period with no issues. Approaching 3 months of SLE data collection. Continuing to work on the reporting dashboard. | Upcoming Activities: Continue to monitor parallel operations. Finalize development of data aggregation tool / reporting dashboard. Finalize draft RZMA. | Open Items:
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
90%
Insert SLAs into ICANN-PTI contract
* All dates are estimates
DRAFT for Discussion
Existing data Parsing conclusions shared
End
parallel testing

## Slide 3: PTI
 | Project | Description | Plan Completion Date | Status | % Complete
 | PTI (Post-Transition IANA) | Formation of PTI entity: legal formation (incorporation of affiliate, filing for 501c3, drafting of contract, etc.) and operationalization of PTI entity (board nominations, budget, etc.). | 09/30/16 08/15/16 |  | 
40%
Project Updates: Drafts of PTI bylaws and articles of incorporation circulated to the community for review. Section headers of Naming function contract circulated to the community for review. PTI formation activities and timing communicated to the community. | Upcoming activities: Finalize PTI Bylaws and articles of incorporation with the community. Share draft of Naming function contract with the community. Share PTI staffing rationale with the community. | Open Items:
05/27/16
Status As Of Date:
DRAFT for Discussion
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
ICANN-PTI contracts ready for public comment
PTI
budget projections
501c3 status ready
ICANN-PTI Contracts Finalized
PTI Implementation Plan defined
Filing for 501c3
1 AoI: Articles of Incorporation / 2CoIP: Conflicts of Interest Policy
PTI Structure activities
Incorporation activities
501 c3 filing activities
ICANN-PTI contracts activities
PTI entity legally
formed
AoI1, CoIP2 and Bylaws ready for Public Comment

## Slide 4: IPR, RZERC, CSC & Escalation Processes
 | Project | Description | Plan Completion Date | Status | % Complete
 | IANA IPR | Transfer of IANA IPR to a neutral trust. |  |  | 
 | RZERC (Root Zone Evolution Review Committee) | Formation of committee to advise ICANN Board on RZMS architectural and operational changes. | 09/30/16 08/15/16 |  | 
 | CSC (Customer Service Standing Committee) | Formation of committee to monitor PTI performance. | 09/30/16 08/15/16 |  | 
 | Escalation Processes | Updating of existing IANA operational complaint and escalation processes. | 09/30/16 08/15/16 |  | 
05/27/16
Status As Of Date:
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
Draft charter ready
CSC constituted
0%
Project Updates: Finalized RZERC charter term sheet with the community. CSC draft request for appointments sent to CWG for review. | Upcoming Activities: Finalize RZERC charter with community and post for public comments. Send request for CSC members and liaisons appointment. Update Escalation processes documentation. | Open Items: Waiting on implementation requirements for IANA IPR.
DRAFT for Discussion
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
55%
70%
50%
RZERC charter drafted &
posted for Public Comment
RZERC charter adopted by ICANN Board
RZERC constituted
CSC
Initial outreach
CSC
constituted

## Slide 5: Enhancing ICANN’s Accountability
 | Project | Description | Plan Completion Date | Status | % Complete
 | ICANN’s Bylaws | Updating of ICANN Bylaws. | 06/09/16 05/27/16* |  | 
 | IRP Enhancements | Implement enhancements to Independent Review Process. | 09/30/16 08/15/16 |  | 
 | RR Enhancements | Implement enhancements to ICANN's reconsideration request process. | 09/30/16 08/15/16 |  | 
 | Empowered Community Enhancements | Implement processes and mechanisms in support of the empowered community. | 09/30/16 08/15/16 |  | 
 | Financial Planning Process Updates | ICANN caretaker budget, PTI caretaker budget and PTI budget. | 08/15/16 |  | 
100%
Project Updates: ICANN Board adopted ICANN bylaws. | Upcoming Activities: | Open Items:
05/27/16
Status As Of Date:
0%
0%
0%
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
Bylaws posted for public comments
ICANN Board adopts Bylaws
DRAFT for Discussion
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
* Assuming a 90-days NTIA inter-agency review period
0%
✔

## Slide 6
Appendix 1
High-Level Projects Plans

## Slide 7: RZMS & SLEs for Naming Community
RZMS & parallel testing activities
Parsing of existing data activities
SLE activities
ICANN-PTI contract activity
DRAFT for Discussion
ICANN determines feasibility of existing data use
ICANN parses existing data (per feasibility determination)
ICANN collects & operationalizes SLE metrics
CWG reviews SLE metrics & defines SLAs
ICANN makes RZMS code changes for SLEs
ICANN develops aggregation tool and SLAs dashboard
ICANN makes RZMS code changes to remove RZA role
Parallel testing
Verisign makes code changes to support parallel testing
ICANN makes RZMS code changes to support parallel testing
Project Updates:
Completed 55 days of 90-day Parallel Testing period with no issues.
Approaching 3 months of SLE data collection.
Continuing to work on the reporting dashboard.
Open Items:
Upcoming Activities:
Continue to monitor parallel operations.
Finalize development of data aggregation tool / reporting dashboard.
Baseline
Current Plan
Status: On-track
% Complete:
70%
* Timeframes are estimates
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
✔
X
Remove NTIA’s authorization process in Production RZMS
✔
✔
✔
✔
Notes: RZMS changes to remove RZA role and support parallel testing: Remove NTIA's authorization process from RZMS (code changes for ICANN and Verisign), and parallel testing
Names SLEs (SLEs for Naming Community): RZMS code changes to accommodate new SLEs, inclusion of performance targets in ICANN-PTI contract, dashboard reporting of SLAs.

## Slide 8: Post-Transition IANA (PTI)
* Timeframes are estimates
DRAFT for Discussion
Define PTI Implementation Plan
Articles of Incorporation drafting, comment period and Board approval
501 (c) (3) filing
ICANN-PTI Contract(s)
Project Updates:
Drafts of PTI bylaws and articles of incorporation circulated to the community for review.
Section headers of Naming function contract circulated to the community for review.
PTI formation activities and timing communicated to the community.
Open Items:
1 Dependency on performance targets being defined by mid-July 2016 under Names SLEs project to finalize Names contract
Upcoming Activities:
Finalize PTI Bylaws and articles of incorporation with the community.
Share draft of Naming function contract with the community.
Share PTI staffing rationale with community.
Public Comment Period
Baseline
Current Plan
Status: on track
% Complete:
40%
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives final proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
Incorporation
Bylaws drafting, comment period, and Board approval
Prepare Financial Projections
Conflict of Interest drafting, comment period, and Board approval
ICANN Board appoints
ICANN’s PTI Board members
File for incorporation
PTI Structure activities
Incorporation activities
501 c3 filing activities
ICANN-PTI contract activity
PTI files for 501c3 status
ICANN-PTI contract(s) drafting, comment period and
Board approval
✔
Notes: Project description: Formation of PTI entity: legal formation (incorporation of affiliate, filing for 501c3, drafting of contract, etc.) and operationalization of PTI entity (board nominations, budget, etc.).

## Slide 9: RZERC (Root Zone Evolution Review Committee)
Implementation plan activity
RZERC charter activities
On-going changes activities
RZERC constitution activities
DRAFT for Discussion
RZERC Charter drafting, public comment period, and Board approval
RZERC formed
ICANN puts in place secretariat support
ICANN coordinates with NTIA on any ongoing architectural & operational changes
Project Updates:
Finalized RZERC charter term sheet with the community.
Open Items:
Upcoming Activities:
Finalize RZERC charter with community and post for public comments.
% Complete:
55%
* Timeframes are estimates
Status: On-track
SO/ACs appoint candidates
ICANN outreach
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
RZERC Formation
RZERC Charter
Public Comment Period
Baseline
Current Plan
Notes: Project Description: Formation of committee to advise ICANN Board on RZMS architectural and operational changes.

## Slide 10: Customer Standing Committee (CSC)
Baseline
Current Plan
DRAFT for Discussion
% Complete:
70%
* Timeframes are estimates
Status: On-track
Project Updates:
Draft request for appointments sent to CWG for review.
Open Items:
Upcoming Activities:
Send request for CSC members and liaisons appointment.
CSC Charter activity
CSC Constitution activities
Operationalization activities
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
ICANN sends SO/AC selected candidates to gNSO/ccNSO
SO/ACs appoint candidates
ICANN outreach
CSC Formation
CSC constituted
Notes: Project Description: Formation of committee to monitor PTI performance.

## Slide 11: IANA Operational Escalation Processes
Baseline
Current Plan
Implementation plan activity
Escalation mechanisms activities
DRAFT for Discussion
Define Implementation Plan
Revise process documentations
Define mediation process for Names community’s IANA Customer Service Complaint Resolution Process
* Timeframes are estimates
% Complete:
50%
Status: On-track
Project Updates:
Open Items:
Upcoming Activities:
Update process documentation
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
✔
Notes: Project description: Updating of existing IANA operational complaint and escalation processes.

## Slide 12: ICANN Bylaws
Transmission of final proposals to NTIA
ICANN Board takes action to post Bylaws for comments
Finalize Bylaws
ICANN Board adopts & notifies NTIA
Public Comment Period
Project Updates:
ICANN Board adopted ICANN bylaws
Open Items:
Upcoming Activities:
DRAFT for Discussion
Status: Complete
% Complete:
100%
* Timeframes are estimates
Bylaws activity
USG activity
Baseline
Current Plan
Prep proposed amendments to ICANN’s Bylaws
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
ICANN Bylaws drafting
✔
✔
✔
✔
✔
Notes: Updating of ICANN Bylaws.

## Slide 13
Appendix 2
RIRs and IETF Status Updates

## Slide 14: RIRs SLAs & IETF MoU Supplemental Agreement
 | Project | Description | Plan Completion Date* | Status | % Complete
 | RIRs SLAs (Service Level Agreement with the Number Community) | Completion of draft agreement, including SLAs with RIRs, and operationalization of SLAs. | 06/30/16 |  | 
 | IETF MoU Supplemental Agreement | Completion of draft ICANN-IETF MoU Supplemental Agreement. | 06/30/16 |  | 
05/27/16
Status As Of Date:
95%
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
IETF MoU Suppl. Doc finalized
RiRs SLAs Document
finalized
IETF MoU Suppl. Doc
signed
Project Updates: ICANN Board approved RIR SLA for signature. ICANN Board approved IETF MoU document for signature. | Upcoming activities: Signing of the RIR SLA document Signing of the IETF MoU document | Open Items:
DRAFT for Discussion
* Completion Date dependent on USG’s approval of proposals
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
95%
RiRs SLAs Document
signed

## Slide 15: RIRs SLA
Baseline
Current Plan
DRAFT for Discussion
Finalize SLA document with RIRs
Board Adoption
Project Updates:
ICANN Board approved RIR SLA for signature.
Open Items:
Upcoming Activities:
Signing of the RIR SLA document.
RIRs SLAs activities
USG activity
Status: On-track
% Complete:
95%
* Timeframes are estimates
Execute SLA document
SLA document becomes effective
IANA contract expires
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
✔
✔
Notes: RIRs SLAs: Completion of draft agreement, including SLAs with RIRs, and operationalization of SLAs.

## Slide 16: IETF MoU Supplemental Agreement (“MoU”)
Baseline
Current Plan
MoU activities
USG activity
DRAFT for Discussion
Finalize MoU document
Board adoption
MoU document becomes effective
Execute MoU document
IANA contract expires
% Complete:
95%
* Timeframes are estimates
Status: On-track
Project Updates:
ICANN Board approved IETF MoU document for signature.
Open Items:
Upcoming Activities:
Signing of the IETF MoU document.
2015
Dec
Jan
Feb
Mar
Aug
Jul
Jun
May
Apr
Nov
Sep
2016
10
NTIA receives proposals
5
ICANN 55
15
Congressional recess starts
27
ICANN 56
30
IANA Contract expires
15
NTIA receives Implementation report
10
NTIA issues report evaluating if conditions are met
✔
✔
Notes: Project Description: Completion of draft ICANN-IETF MoU Supplemental Agreement.

## Slide 17
Appendix 3
Post Transition Projects

## Slide 18: Post Transition Projects
 | Project | Description
 | IANA Remedial Action Procedures | New remediation process for the CSC to address poor performance with IANA before escalation to the ccNSO/GNSO. To be finalized between CSC and IANA post transition. (CWG)
 | IANA Function Review (IFR) | Review of PTI’s performance against the ICANN-PTI contract and SOW. First IFR to take place 2 years after transition. (CWG)
 | Special IFR | To be initiated when CSC remedial action procedures and IANA problem resolution process are followed and failed to correct deficiency. (CWG)
 | Separation Cross Community Working Group (SCWG) | To be formed if the special IFR results in a recommendation for separation. (CWG)
 | Transition to Successor IFO | Plan for Transition to Successor IFO. (CWG)
 | Formal study on changes to root zone content | To investigate whether there is need to increase the robustness of the operational arrangements for making changes to the root zone content to reduce or eliminate single point of failure. (CWG)
 | CCWG-Accountability Work Stream 2 | To commence at ICANN55 and complete by end of 2016; WS 2 elements include: Diversity, SO/AC accountability, Transparency, Human Rights, Jurisdiction, Interim Bylaw. (CCWG)
−
−
−
−
−
−
−