## Slide 1
2017/8 ccNSO Review: An Overview
Lars Hoffmann | Webinar | 6 February 2017

## Slide 2: Possible Road Map for ccNSO Review
Draft RFP for ccNSO feedback
Apr-May
June
RFP Launched
July
Sep
Select Ind. Exam; Launch Review
Sep-Mar
Interviews, Survey, Analysis
Mar
Draft Report for WP
Jun
Final Report for WP
Final Report
ICANN58
ICANN61
Review plans continuously aligned with community workload and flexibility to accommodate extensions, when necessary.
2017 2018
12 Dec 2016
ICANN59
April
Public Comments
ICANN60
Mar
OEC Chair-ccNSO Meeting
ICANN62
Orange indicates WP ‘work phases’

## Slide 3: Roles and Responsibilities
Review Working Party
  Liaison
  Conduct self-assessment
  Help tailor review methodology
  Input into review scope, deliverables and selection criteria
  Community outreach support
  Input into data collection – online assessment and interviews
  Provide clarification and factual corrections
  Assess usefulness & feasibility of recommendations
  Assess effectiveness of prior review improvements
  Review of documents, records
  Observe proceedings
  Develop and conduct online surveys
  Conduct interviews
  Factual observations and implementable recommendations
  Engage with stakeholders for clarification and correction
  Prepare report(s)
  Oversight
  Scope of review
  Confirm Independent Examiner
  Accept Report*
  Approve Implementation Plans*
  Monitor progress of implementations
Independent Examiner
ICANN Org.
  Prepare RFP, run competitive bidding process
  Monitor timeline and resources
  Support review
  Support outreach and engagement
  Manage report and public comment process
  Assist with preparation of Review Implementation Plan
OEC
*Prepare Recommendations for Board Action
Independent Examiner

## Slide 4: Next step: RFP and Scope
You can find all information on 2009 ccNSO Review, including the RFP, Review Team composition, and Final Report here:
https://www.icann.org/resources/reviews/org/ccnso (or search for ‘ccnso review’)
The Request for Proposal is the ‘call for an independent examiner’
The RFP, among others, sets the scope of review
The OEC is the ultimate arbiter of the scope but ICANNorg works very closely with the community under review to assure the scope meets everyone’s expectations
Bylaws prescribe at a minimum:
The goal of the review, to be undertaken pursuant to such criteria and standards as the Board shall direct, shall be to determine (i) whether that organization, council or committee has a continuing purpose in the ICANN structure, (ii) if so, whether any change in structure or operations is desirable to improve its effectiveness and (iii) whether that organization, council or committee is accountable to its constituencies, stakeholder groups, organizations and other stakeholders.
During ICANN58 a meeting with the OEC will take place to set expectations with regard to scope

## Slide 5: Questions and Answers
Reach us at:
Email: lars.hoffmann@icann.org
Website: icann.org/resources/reviews/org
Thank You and Questions
Notes: You can adjust the email/web address to whichever email or web address is best suited to your presentation. This should be your final slide.