## Slide 2
GNSO Working Session
GNSO Council | ICANN58 | 12 March 2017

## Slide 3: Agenda
IGO-INGO Curative Rights PDP
Next-Gen RDS PDP
New gTLDs Subsequent Procedures PDP
RPM Review PDP
Privacy/Proxy Accreditation IRT
Discussion of motions
1
2
3
4
5
6

## Slide 4
1. IGO-INGO Access to Curative Rights Protections PDP
Philip Corwin and Petter Rindforth

## Slide 5: OVERVIEW: Project Timeline & Major Milestones
Nov
2013
Jun
2014
Jan – Apr 2015
Oct 2015 – Nov 2016
ICANN58
?
Timing may align with completion of outstanding GAC-GNSO discussions on IGO acronym protections
Original GNSO PDP: Some preventative protections recommended
Issue Report on IGO-INGO curative rights recommended
This PDP initiated on IGO-INGO curative rights
PDP WG solicits early input from all SO/ACs
Input received from SSAC, GAC, several GNSO SG/Cs, and IGOs
PDP WG consults external legal expert
PDP Working Group reviews IGO Small Group Proosal
PDP WG completes Final Report
Jan 2017
PDP WG publishes Initial Report for Public Comment (closing 30 March 2017)
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 6: What are the current challenges & issues under discussion? (1/2)
Ongoing Board-facilitated GAC-GNSO dialogue on IGO acronym protections is broader than this PDP scope but includes curative rights topics
  IGO Small Group Proposal includes both preventative and curative rights recommendations
  But within the GNSO, issues relating to Curative Rights and Preventative Protections have been dealt with under distinct GNSO processes (i.e. two separate, sequential PDPs)
  However, WG recognizes that IGOs deserve meaningful curative rights protections that allow preventative protections (e.g. IGO notified when a third party registers a domain matching the IGO’s acronym) to be effective
Final outcome and timing of reconciliation of GAC advice and adopted GNSO policy unclear
  Any agreed principles from the facilitated discussions need to be reviewed and approved through the respective GAC and GNSO processes – takes time and may require public comment
  These must still be factored into the final recommendations from this PDP
Current PDP recommendations differ from IGO Small Group Proposal
  WG beginning to review public comments received

## Slide 7: What are the current challenges & issues under discussion? (2/2)
Working Group’s preliminary recommendations differ from the IGO Small Group Proposal supported by governments:
  Small Group Proposal is for:
    Post-registration notice only to an affected IGO when a third party registers a domain matching or containing the IGO acronym (no pre-registration notice to a potential registrant);
    Separate dispute resolution procedure (appealable via arbitration)
    Rapid relief mechanism modeled after the URS
  Preliminary PDP recommendations are:
    No new dispute resolution procedure
    No essential substantive changes to the UDRP and URS
    No change to Mutual Jurisdiction clause of UDRP and URS:
      Standing to file to be shown by an IGO’s having followed the requisite notification process under Article 6ter of the Paris Convention for the Protection of Industrial Property - broadening the scope and availability of UDRP/URS to IGOs
      Recommendation made based on external legal expert opinion that there is no uniform international law on IGO jurisdictional immunity

## Slide 8: How can the GNSO Council & ICANN community assist?
GNSO Delegation participating in Board-facilitated GAC-GNSO dialogue on reconciling inconsistent GAC advice and previously-adopted GNSO policy (from the 2013 IGO-INGO PDP)
  Preventative protections (including any potential modification of the original 2013 PDP recommendations) should be aligned with appropriate curative rights mechanisms
    However, any final solution regarding adequate IGO protections in all gTLDs should include consideration of the deliberations and recommendations from this PDP
Monitoring and managing timelines for the two work tracks – ongoing reconciliation of inconsistent advice and completion of this PDP
  Timely community input for consideration by the Working Group in preparing its Final Report will be very helpful
  Note that implementation of any and all final solutions may need to be integrated into a third, ongoing work track – implementation of the preventative protections from the original 2013 PDP – for efficiency and consistency

## Slide 9: Sessions at ICANN58 and Further Information
Open Working Group community session on Wednesday 15 March 2017, 1345 – 1500, Hall B4.2: http://sched.co/9nms
Background information: https://gnso.icann.org/en/group-activities/active/igo-ingo-crp-access
ICANN58 Background Briefing Paper: https://gnso.icann.org/en/issues/policy-briefing-igo-ingo-crp-access-27feb17-en.pdf
Working Group online wiki space (with meeting transcripts, call recordings, draft documents and background materials): https://community.icann.org/x/37rhAg

## Slide 10
2. Next-Generation gTLD Registration Directory Services PDP
Chuck Gomes

## Slide 11: RDS PDP: Project Timeline & Major Milestones
Apr 2015 Board Resolution
Nov 2015
Charter Approval
Jan 2016 Phase 1 WG Formed
Jun 2016 Possible Req’ts List
Nov 2016
Deliberation Begins
TBD 2017 First Initial Report (P1)
Next Steps:
Second Initial Report (Phase 1)
Final Report (Phase 1)
If a next-gen RDS is needed:
Phase 2 (Policy Development)
Phase 3 (Implementation and Coexistence Guidance)
In April 2015, the ICANN Board reaffirmed ‘its request for a Board-initiated GNSO policy development process to define the purpose of collecting, maintaining and providing access to generic top-level domain (gTLD) registration data, and consider safeguards for protecting data, using the recommendations in the Expert Working Group (EWG) Final Report as an input to, and, if appropriate, as the foundation for a new gTLD policy’.
Following publication of the PDP Final Issue Report, the GNSO Council adopted the charter for the PDP WG, which commenced its deliberations at the end of January 2016. During the first phase its work, the WG has been tasked with providing the GNSO Council with recommendations on the following two questions:
1) What are the fundamental requirements for gTLD registration data? 2) Is a new policy framework and next-generation registration directory services (RDS) needed to address these requirements?
WHAT THIS PROJECT IS ABOUT

## Slide 12: What are the current challenges & issues under discussion?
Issues now under discussion: Phase 1 deliberation on Fundamental Requirements for 3 charter questions:
  Users/Purposes: Who should have access to gTLD registration data and why?
  Data Elements: What data should be collected, stored, and disclosed?
  Privacy: What steps are needed to protect data and privacy?
Initial points of rough consensus reached since ICANN57 are reflected in our working document
Current challenges include burnout, complexity, duration, and conflicting views
  When agreeing upon individual requirements proved difficult, we refocused on “Key Concepts”
  To find common ground, we narrowed the focus of initial deliberation to “thin data” and collection

## Slide 13: How can the GNSO Council & ICANN community assist?
At ICANN58, sessions with data commissioners may help us better understand key data protection and privacy concepts, so that our WG can apply them to registration data & directory services.
As Key Concepts are identified by our WG, we are using polls to confirm rough consensus & identify next steps. GNSO SGs/Cs and ACs/SOs can assist by encouraging their members who participate in this PDP to participate in meetings and polls, keep an open mind, listen to each other, and be willing to consider compromises.
When this WG posts its First Initial Report for public comment, GNSO SGs/Cs and ACs/SOs can assist by providing robust feedback on WG-identified possible requirements pertaining to RDS Purpose, Data Elements, and Privacy.

## Slide 14: Sessions at ICANN58 and Further Information
Open Working Group meeting/community sessions: Saturday 11 March 13:45 CET: http://sched.co/9npN and Wednesday 15 March 13:45 CET: http://sched.co/9npc
Background information: Background Docs: https://community.icann.org/x/QIxlAw Phase 1 Docs: https://community.icann.org/x/p4xlAw
ICANN58 Background Briefing Paper: http://gnso.icann.org/en/issues/policy-briefing-next-gen-rds-27feb17-en.pdf
Working Group Charter: https://community.icann.org/x/E4xlAw
Working Group online wiki space (with meeting transcripts, call recordings, draft documents and background materials): https://community.icann.org/x/rjJ-Ag

## Slide 15
Additional Slides

## Slide 16: Initial points of rough consensus (iterative deliberation on-going)
Should gTLD registration thin data elements be accessible for any purpose or only for specific purposes?
    The WG should continue deliberation on the purpose(s) of "thin data."
    Every "thin data" element should have at least one legitimate purpose.
    Every existing "thin data" element does have at least one legitimate purpose for collection.
For what specific (legitimate) purposes should gTLD registration thin data elements be collected?
    EWG-identified purposes apply to at least one "thin data" element.
    Domain name control is a legitimate purpose for “thin data” collection.
    Technical Issue Resolution is a legitimate purpose for “thin data” collection.
    Domain Name Certification is a legitimate purpose for "thin data" collection.
    Business Domain Name Purchase or Sale is a legitimate purpose for "thin data" collection.
    Academic / Public Interest DNS Research is a legitimate purpose for "thin data" collection.
    Regulatory and Contractual Enforcement is a legitimate purpose for "thin data" collection.
    Criminal Investigation & DNS Abuse Mitigation is a legitimate purpose for "thin data" collection.
    Legal Actions is a legitimate purpose for "thin data" collection.
    Individual Internet Use is a legitimate purpose for "thin data" collection.

## Slide 17: Initial points of rough consensus (iterative deliberation on-going)
For thin data only -- Do existing gTLD registration directory services policies sufficiently address compliance with applicable data protection, privacy, and free speech laws within each jurisdiction?
    Existing gTLD RDS policies do NOT sufficiently address compliance with applicable data protection, privacy, and free speech laws about purpose.
    As a WG, we need to agree upon a purpose statement for the RDS.
What should the over-arching purpose be of collecting, maintaining, and providing access to gTLD registration (thin) data?
    A purpose of gTLD registration data is to provide info about the lifecycle of a domain name.
    A purpose of RDS is to identify domain contacts and facilitate communication with domain contacts associated with gTLDs, [based on approved policy]
    A purpose of gTLD registration data is to provide a record of domain name registrations
    A purpose of RDS policy is to facilitate the accuracy of gTLD registration data

## Slide 18: Phase 1 Workplan
Currently, we are working on Task 12) Deliberating on Fundamental Requirements for:
  Users/Purposes
  Data Elements
  Privacy
  Gated Access
  Data Accuracy
Our First Initial Report will be published in Task 13), attempting to answer the Foundational Question:
  "Is a new next-gen RDS needed or can the existing WHOIS system be modified to satisfy fundamental requirements?”

## Slide 19: Phase 1 approach to reach consensus
FQ
First Initial Report
Public Comment
Rough Informal Consensus
Second
Initial Report
Public Comment
CX
CM
SM
CS
BE
RI
Consensus
Final Report
Phase 1
Formal Consensus per Charter IV
UP
DE
PR
12a&b
GA
DA
OQ
12c&d
12e
13
14
18
19
20
15-16
Task #s are taken from Work Plan @ https://community.icann.org/x/oIxlAw
FQ Foundational Question
OQ Other Questions
UP Users/Purposes
GA Gated Access
DA Data Accuracy
DE Data Elements
PR Privacy
CX Coexistence
CM Compliance
SM System Model
CS Cost
BE Benefits
RI Risks

## Slide 20
3. New gTLD Subsequent Procedures PDP
Avri Doria and Jeff Neuman

## Slide 21: Timeline
Mar
2017
June
2017
Sept
2017
Dec
2017
Feb
2018
Sept
2018
Send CC2 to SO/AC/SG/Cs
Complete preliminary WT deliberations
Consider CC2 input and consider WT recommendations at plenary level
Publish Initial Report for public comment
Publish summary of public comment
This PDP was chartered by the GNSO Council in January 2016 to consider the experiences from the 2012 round of the New gTLD Program to determine what additions or modifications are needed for the existing new gTLD policy recommendations.
What this Project is About
Complete Final Report
Next
Steps
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 22: What are the current challenges & issues under discussion?
The WG is establishing 3 drafting teams to cover overarching issues. The WG is also broken into 4 Work Tracks to address the remaining subjects within its charter.
Biggest Issues:
  Extensive list of subjects in charter that must all be considered
  Parallel work within the community on topics within scope of this PDP (e.g., geographic names, community applications, etc.)
  Interconnected efforts (e.g., RPMs, CCT-RT, CWG-UCTN, etc.) can make it difficult to stay coordinated and informed

## Slide 23: How can the GNSO Council & ICANN community assist?
Provide support in coordinating parallel tracks within the community.
Help encourage community participation from the GNSO and beyond.

## Slide 24: Sessions at ICANN58 and Further Information
Meetings
Face to face session on 11 March: recordings will be available here - http://sched.co/9nmb
New gTLD Program Reviews on 13 March from 15:15-16:45: http://sched.co/9no3
Community dialogue session on 15 March from 17:00-18:30: http://sched.co/9sZB
Resources
GNSO Project Page: https://gnso.icann.org/en/group-activities/active/new-gtld-subsequent-procedures
WG Wiki: https://community.icann.org/x/RgV1Aw
WG Charter: https://gnso.icann.org/en/issues/new-gtlds/subsequent-procedures-charter-21jan16-en.pdf
WG Work Plan: https://community.icann.org/x/NAp1Aw

## Slide 25
Appendix A: WG Subjects
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 26: WG Subjects

## Slide 27: WG Subjects, cont.

## Slide 28: WG Subjects, cont.

## Slide 29
4. Review of all Rights Protection Mechanisms in all gTLDs PDP
Kathy Kleiman, Philip Corwin, and J. Scott Evans

## Slide 30: OVERVIEW: Project Timeline & Major Milestones
Mar
2016
Jun 2016 (ICANN56)
Nov
2016 (ICANN57)
Mar 2017 (ICANN58)
Jun 2017 (ICANN59)
Oct 2017 (ICANN60)
Publish Phase One report for Public Comment (end-2017/early 2018)
Commence Phase Two (Uniform Dispute Resolution Policy; early 2018)
WG chartered by GNSO Council
Community discussion of Charter/PDP scope
Complete Trademark PDDRP initial review; discuss TMCH Charter questions
TMCH review ongoing; discuss plan to start Sunrise & Claims review
Completing Claims Notice initial review
This PDP was chartered by the GNSO Council to review all the Rights Protection Mechanisms (RPMs) that are currently in operation
Phase One focuses on the RPMs created for the 2012 New gTLD Program
Phase Two on the 1999 Uniform Dispute Resolution Policy (which applies to all gTLDs).
WHAT THIS PROJECT IS ABOUT
Completing Uniform Rapid Suspension initial review
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 31: What are the current challenges & issues under discussion?
Timelines remain aggressive, though not unreasonable
  Phase One needs to be completed prior to launch of next expansion round
Need to coordinate with other parallel efforts
  E.g.: the ongoing PDP on New gTLD Subsequent Procedures
  Current need to review recent Final Report on Trademark Clearinghouse (TMCH) Independent Review
Continuing need to obtain reliable data
  Not clear that all sources will necessarily be able or willing to provide needed data (e.g. confidentiality issues); lack of response to initial outreach to SO/AC/SG/Constituencies (with some exceptions)
PDP deals with complex issues where there are likely to be strong and divergent views
  Especially on longstanding issues that have divided parts of the community since the topic of trademark protection was first identified as an overarching issue for the 2012 New gTLD Program
Large numbers of Members and Observers, but not clear that more than a core number are able to participate actively or regularly
  Likely increase in use of Sub Teams may exacerbate this problem

## Slide 32: How can the GNSO Council & ICANN community assist?
Working Group has identified data gathering (possibly including professional survey design) as a priority
  This may require budget and additional resources (e.g. using the new GNSO Data & Metrics Request process)
Working Group will be seeking information periodically from Service Providers, Registries, Registrars, Registrants and other ICANN SO/ACs
  Need to minimize too many outreach requests and manage their timing, important that affected users provide responses
Working Group to review need for additional face to face meetings to complete Phase One
  GNSO Council requested to give any such request from the Working Group due consideration
Working Group to consider how to best use Council and community liaisons
  GNSO Council can provide guidance on how Council and community liaisons should function

## Slide 33: Sessions at ICANN58 and Further Information
Open Working Group meeting/community session on Wednesday 15 March 2017, 0900 – 1030, Hall C1.4: http://sched.co/9npd
Background information: https://gnso.icann.org/en/group-activities/active/rpm
ICANN58 Background Briefing Paper: https://gnso.icann.org/en/issues/policy-briefing-rpm-review-27feb17-en.pdf
Working Group Charter: https://community.icann.org/x/2CWAAw
Working Group online wiki space (with meeting transcripts, call recordings, draft documents and background materials): https://community.icann.org/x/wCWAAw

## Slide 34
5. Privacy and Proxy Services Accreditation IRT
Darcy Southwell

## Slide 35
Background/Project Status

## Slide 36: Overview
Project Summary: Privacy and Proxy Service Provider Accreditation Program IRT is working with the ICANN organization to implement a new accreditation program pursuant to Final PDP Recommendations.
Impact: This new accreditation program will impact Registrants, P/P Providers, Registrars and Third Parties who use the Registration Data Directory Service to locate information about and contact Registrants.
Benefits: Benefits of this new program will include increased consistency/predictability among P/P Providers’ practices and Compliance enforcement of contractual requirements.

## Slide 37: Project Background
Final Recommendations adopted by GNSO Council in January 2016
ICANN Board approved Final Recommendations 9 August 2016
Implementation Review Team convened in October 2016
IRT meets weekly, on Tuesdays at 15:00 UTC

## Slide 38: IRT Accomplishments
Relatively large IRT (43 members) has been very active (50%+ present at each meeting)
IRT has had 10 working meetings (plus half-day session at ICANN58)
IRT has:
  discussed all of ICANN org’s initial questions related to the Policy document;
  reviewed proposal on WHOIS labeling;
  reviewed proposals on data retention and escrow; and
  provided input to ICANN on initial operational questions.
Notes: The IRT has completed a significant amount of work in a very short period of time. Current pace of project requires significant volunteer resources, but volunteers seem to be keeping up.

## Slide 39
Project Timeline
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 40: Project Timeline
Originally projected Policy Effective Date: 1 January 2019
Increased pace, at IRT recommendation, to better align with expiration of interim Registrar Accreditation Agreement specification (1 January 2018)
Estimated posting of draft Policy and Contract for public comment: September 2017
Final announcement date will depend on extent of changes needed based on public comments
Will assess timeline status quarterly
Notes: Use this slide for diagrams or other graphic elements.

## Slide 41: Steps to Public Comment: Projected
March 2017
April
2017
May
2017
June
2017
July
2017
August
2017
Public Comment
Review of Policy Document
Policy Review; Contract Questions
LEA Framework; De-Accreditation/Transfers
Contract Review
Contract Review
Finalize Materials for Public Comment
Notes: Topics we know must be covered in the IRT before Policy document and contract can be posted for public comment:
>Review/Discussion of v2 Policy document (initial discussion on high-level questions complete)
>Review/discussion of PPAA (currently being drafted by ICANN org)
>Development of LEA disclosure framework (initial proposal in development by GAC PSWG)
>Discussion of Transfer issues and de-accreditation processes
Based on our current pace, we may be able to finish these topics and be ready for public comment in late August or early September. However, this timeline is only an estimate and will be impacted by the length of IRT discussions on particular topics and, possibly, external factors (if additional work is added on Transfer Policy, for example, this could impact timeline).

## Slide 42: Privacy/Proxy IRT Timeline (updated February 2017)
Mar
Apr
May
Jun
Nov
Oct
Sep
Aug
Jul
ICANN Drafting: PPAA
LEA Proposal Drafting
IRT Policy Review
IRT Review: PPAA
Public Comment Period
Final Program Announced; Operational and Compliance Readiness (will extend into 2018)*
Jan
Feb
Dec
* Timing could be impacted significantly by scope of work required after public comment period.
Notes: This is an extended timeline showing steps after public comment. The actual implementation date of this program will be impacted heavily by the scope of changes required based on public comments. This timeline would reflect a scenario where there are very few changes required—more significant, substantive changes could take additional time.

## Slide 43: Engage with ICANN
IRT wiki: https://community.icann.org/display/IRT/Privacy+and+Proxy+Services+Accreditation+Implementation
Thank You and Questions
linkedin.com/company/icann
twitter.com/icann
facebook.com/icannorg
weibo.com/ICANNorg
youtube.com/user/icannnews
slideshare.net/icannpresentations
flickr.com/photos/icann
soundcloud.com/icann
Notes: You can adjust the email/web address to whichever email or web address is best suited to your presentation. This should be your final slide.

## Slide 44
6. Discussion of Motions
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 45: Motion – Preliminary Adoption of GNSO Standing Selection Committee (SSC) Charter
Full language of the motion is available at https://community.icann.org/x/lJvRAw
Resolved,
The GNSO Council adopts the GNSO Standing Selection Committee (SSC) Charter on an interim basis (see [include link] and instructs the GNSO Secretariat to launch a call for volunteers per the membership criteria outlined in the SSC Charter as soon as possible with a view to establishing the SSC no later than X date.
The GNSO Council tasks the SSC to carry out the review and selection of GNSO endorsed candidates for the Registration Directory Service Review Team for Council consideration at the latest by its 20 April 2017 meeting.
The GNSO Council tasks the SSC to develop the criteria and the process for the selection of the GNSO Representative to the Empowered Community for GNSO Council consideration by its June 2017 meeting, and following the approval by the GNSO Council, carry out the selection process.
Following the completion of two selection processes , the GNSO Council requests the SSC to report back to the GNSO Council with its assessment of whether the charter provides sufficient guidance and flexibility to carry out its work, and/or whether any modifications should be considered.
The GNSO Council thanks the small group of volunteers, Susan Kawaguchi, Ed Morris and the GNSO Council leadership team, for its work on the charter.
Notes: Use this slide for diagrams or other graphic elements.