## Slide 1: Proposed Methodology Working Group Retirement ccTLDs

## Slide 2: Issue Report PDP
Issues to be addressed through PDP
Working method (Task Force or other)
  Two Working Groups
General Counsel opinion
  In scope of ccNSO PDP (Annex C)
  Lasting value
Required request advice or opinion GAC
  Just received
Overall schedule of deliverables and timeline
Charters WG retirement and review mechanism
Currently Public comment
  requirement Annex B
  Until 10 July (no comment received)
  Provide input to work of this WG

## Slide 3: Charter Retirement WG
Charter included in issue report
  Drafted by community
Section Scope and high level description of issues to be addressed
Deliverables
Membership
Working method
Tentative Timeline

## Slide 4: Deliverables
WG deliverables
  Interim paper (including at least one public comment)
  Final Paper
  Progress reports
  Updates to ccNSO Council
Public comment on Interim paper ( at least 40 days)
  If required additional round of public comment
Final Paper to be included in Interim Report Issue Manager
  Will also include final paper on review mechanism
  Public comment (at least 40 days)

## Slide 5: Timeline
Activity | Date (tentatively) | Closure | Minimum Duration
Create Working Group |  | Completed 15 May, awaiting participants GAC and other groups | 
Develop Interim Paper | June 2017 | November 2017 | 4 months
Public Comment on Interim Paper | November 2017 | Late December 2017 | 2 months
Develop Final Paper | January 2018 | March 2018 | 2 months
Closure of the WG |  |  | 

## Slide 6: Membership
Members
  Related to ccTLD managers
  ccNSo Council appointed
Participants
  Appointed/ participate through other SO/AC’s
  ALAC, GNSO
  Awaiting GAC and SSAC, if any
Observers
Experts
  PTI/IANA
  ISO 3166

## Slide 7: Working Method
Call every two weeks
  1 hour – 1.5 hour
  Rotational basis
  Transcripts of call (if needed)
Issue Manager/staff provide strawman documents
Provide comments on-line
  (one week after call)
Redline versions to be circulated 3 business days for the next meeting
Adopt only after two readings
Consensus decision making (“die in the ditch” criterion)
  By full group
  Only if vote needed: members only
Engage broader community at f-2-f meetings

## Slide 8: Next steps
WG to nominate chair & vice chair
  In two weeks
  To be appointed by the ccNSO Council
Kick-off discussion
  Explanation of “un-assignment of codes” in ISO 3166 terms & terminology in use
  Overview of cases
Face to face meeting ICANN 59
  When: Thursday, 29 June
  Time: 1030-1200 local time (block 2)
  Room: Committee 2
  Remote participation: https://participate.icann.org/jnb59-committeeroom2

## Slide 9: Tools
PDP Retirement WG webpage
  https://ccnso.icann.org/workinggroups/pdp-retirement.htm
  List of membership
  Background material
  Static information
PDP Retirement Wiki space
  https://community.icann.org/display/ccnsowkspc/Policy+Development+Process+%28PDP%29+-+Retirement
  To be used to keep WG and broader community abreast what is going on
  Repository working documents
Conference calls
  Adigo bridge
  Dedicated Adobe room
  Transcripts (if requested/needed)