## Sheet1
Date asked | Asked by | Related Topic | Question | Answer | Expected delivery date | Date answered | Notes
2017-10-09 | Denise Michel during briefing | Risk Management | Please provide in writing details on how the risk management framework responsibility has been staffed at ICANN since the SSR1 recommendations were adopted by the Board. | Board Risk Committee, Risk Management Committee made up of the ICANN org executive team which provides oversight, VP Risk Management, Function Risk Liaisons who are staff members who represent each function for implementing the risk framework, and all organization personnel who own the risks inherent in their activities. |  | 2018-09-28
2017-10-09 | James Gannon during briefing | Risk Management | Do business continuity testing tabletop exercises for PTI occur at a more regular frequency and to a deeper level than the standard for the rest of ICANN? | Historically, dedicated continuity exercises have been conducted for the root zone management component of the IANA functions with our root management partners. In addition, the ICANN org has conducted exercises for the shared IT systems and services that support the IANA functions. Since the creation of PTI we have not had a dedicated PTI-specific continuity exercise. We seek to develop a plan to conduct future exercises once we restore a full complement of staff following recent personnel changes. |  | 2018-11-05
2017-10-09 | Denise Michel during briefing | Risk Management | Is there a final DNS Risk Assessment document? (the one shared is marked “draft” and dated May 28, 2014) | There is no final document. DNS risk is included in ICANN’s overall risk management. |  | 2018-09-28
2017-10-10 | Denise Michel via email | EBERO | Please provide information on compliance action relating to EBERO | Details regarding the triggers and process for an emergency transition of a registry are set forth in Section 2.13 of the registry agreement and the transition process at https://www.icann.org/resources/pages/transition-processes-2013-04-22-en . As with any contractual obligation, Contractual Compliance enforces the critical registry functions and the emergency thresholds in Section 6 of Specification 10 of the registry agreement, which can lead to such transition. There has been no compliance action against an Emergency Back End Registry Operator to date. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | EBERO | Please provide information on data escrow providers” contractual obligations/requirements and actions taken by ICANN Org. to monitor and ensure compliance with these obligations | Contractual Compliance data escrow ongoing activities are to ensure registry operators are complying with data escrow provisions of registry agreement per Section 2.3 and Specification 2 and that Registrars are complying with the Registrar Data Escrow Specification https://www.icann.org/en/system/files/files/rde-specs-09nov07-en.pdf . The data escrow providers’ contractual obligations/requirements are monitored by the Global Domains Division team to ensure compliance with their obligations (vendor management role). | 2018-12-14 | 2018-12-11
2017-10-09 | Denise Michel during briefing | EBERO | What is the ETA on the planned public webpage that will include some high-level data from the SLA Monitoring System? | Producing the webpage is in the roadmap, but it currently does not have an ETA. It is dependent on the ODI initiative, among other things that have yet to be done. |  | 2018-11-06
2017-10-09 | Unidentified during briefing | EBERO | Please share the presentation about testing potential EBERO events from end to end. | https://schd.ws/hosted_files/icann60abudhabi2017/08/7%20EBERO%20Arias.pdf |  | 2018-11-05
2017-10-09 | Eric Osterweil during briefing | EBERO | Please provide a link to the presentations regarding RCA’s requested in EBEROs / documentation of standard issues. | https://schd.ws/hosted_files/icann60abudhabi2017/08/7%20EBERO%20Arias.pdf |  | 2018-11-05
2017-10-09 | Denise Michel during briefing | Domain Abuse Activity Reporting (DAAR) | We’ve been told that this particular contract that supported ICANN’s gathering of this data does not allow it to display all of this data. Once ICANN understands what can and cannot be displayed, will they come back to the Board and community with the cost to report on everything? What would a new contract with a new provider potentially, or the same provider, need to look like in order to display more of that particular data publicly, and what would it cost? | There are two things conflated here. One is the cost of curating and validating the the data. This is the major cost and is covered by ICANN's budget transparency. The other is the cost of then defining which of the curated data we can publish and presenting that to the public. It is ICANN's intention to publish as much data that our licensing allows via ODI. This cost is not yet certain as we have not finalized the possible output but it is likely to be minimal. |  | 2018-11-12
2017-10-10 | James Gannon during briefing | ICANN security | Is there a reason why ICANN does not use more industry-standard, certifiable and auditable processes, per SSR1 recommendation 9, instead of custom processes? | The ICANN org uses a suite of continuous improvement frameworks to drive improvement across the organization. This includes the use of audit and certification frameworks for Engineering and IT, and IANA functions, and EFQM as a holistic framework for assessing and improving the whole organisation. |  | 2018-11-05
2017-10-10 | Norm Ritchie during briefing | ICANN security | Given the relative importance of IANA.org - because if you have to reach out to it to do any automated changes to a TLD zone, you have to be able to reach it - what is the resiliency for IANA.org to maintain? Is it given any special attention? | All zones hosted by ICANN have maximum resiliency none are given a special tier of service. We have redundant infrastructure to make sure the zone management and propagation as well as signing can always occur. We also maintain a robust ANYCAST network for serving up the zones hosted by ICANN. That being said, if something were to occur that required a zone by zone recovery, IANA.org would be near the top of the list. | 2018-12-14 | 2018-12-11
2017-10-10 | Norm Ritchie during briefing | ICANN security | Who administrates IANA-servers.net, and any process behind that? | ICANN DNS Engineering and Operations administers IANA-servers.net, it is servered up by ICANN, ISC and AFILIAS in the form of: a.iana-servers.net, b.iana-servers.net, c.iana-servers.net | 2018-12-14 | 2018-12-11
2017-10-10 | James Gannon during briefing | ICANN security | Expanding away from just IANA.org, there is a lot of “critical operations stuff”, the GDD portal and some of the other supporting infrastructure. Is that managed just as a general ICANN service or is attention given to the supporting infrastructure that sits around the root zone maintenance? And is that just handled as a general ICANN IT service? | Root zone administration is handled with the same care as all ICANN critical infrastructure, redundant systems, site failover, quick restore as well as enforcement of application security best practices. We can’t speak to the RZM (Root Zone Maintainer as that function is handled by Verisign). As for the GDD portal itself, that is a service hosted by Salesforce. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel during briefing | ICANN security | Several months ago, some DNS attacks and defense occupied a lot of attention, with attacks jeopardizing some of the root zone servers. How do you feel the state of things are and can you elaborate on about steps that were taken, both by ICANN and by the community in response to that? | Even though the Root Server operated by ICANN was not affected we made some changes after the last round of DDOS attacks against the root. We increased bandwidth in our core cluster sites (10G to each server) in order to have large sink holes for traffic as we remove announcements from affected single servers. Another side effect of the last DDOS was even more collaboration with other RSO's. All of these changes will make us better able to handle and mitigate the next round of DDOS attempts. ICANN DNS Engineering is continuously improving our tooling to more quickly address attacks or failures of any sort. | 2018-12-14 | 2018-12-11
2017-10-10 | Noorul Ameen during briefing | ICANN security | Is there any meta data available on DNS traffic surveillance? |  | 2019-01-25
2017-10-10 | Denise Michel during briefing | Compliance | Is an NDA required to obtain information on which registrars have the highest WHOIS inaccuracy rates currently? |  | 2019-01-25
2017-10-10 | Denise Michel during briefing | Security incident management | Please share the links to security incident reporting information on ICANN.org. | https://www.icann.org/news/blog/transparency-of-security-efforts-in-icann https://www.icann.org/en/system/files/files/vulnerability-disclosure-05aug13-en.pdf https://www.icann.org/news/blog/ciio-perspectives-icann-s-incident-response-protocol |  | 2018-11-05
2017-10-10 | Norm Ritchie, Eric Osterweil during briefing | Security incident management | We want to understand the extent to which there’s breachability or dependencies that exist between systems and repositories that support either IANA’s operations, its systems, its registries or anything else with other things that are managed in the corp IT infrastructure. Is there any sort of compartmentalization, are there any boundaries, protections in place to isolate various pieces? Eg. to protect a beachhead from reaching what services the global identifier system in some way. | ICANN Org employs network segmentation strategies designed to reduce the risk of pivoting activity by an attacker. Administrative access to critical services (particularly those managed by IANA) have restrictions beyond internal network access. Periodic network penetration testing is conducted by independent service providers against ICANN Org network defenses, simulating attacks from both outside the network and attempted lateral movement from within the network. The results are used to prioritize network security Improvements. | 2018-12-14 | 2018-12-11
2017-10-10 | Noorul Ameen during briefing | Security incident management | If you consider incident handling, there are two kinds of processes. One is internal incident handling process, and the second thing is that global issues. An example would be if you have a squatted domain similar to ICANN.org or .com, the incident handling procedure would be different because the entities involved are different groups. And if you have a targeted attack or a scanning attack on your website, that is your internal issue. Do you have any policy to distinguish between these two kinds of incidents? Is it the same team or the same kind of process you have following for both incidents? |  | 2019-01-25
2017-10-10 | Noorul Ameen during briefing | Security incident management | This is regarding the reactive handling of a particular incident. Suppose you’re observing any kind of probes or attack from a particular country IP. So for country X handling procedure is to contact IP owner or the domain owner of that IP and you need to report it to the corresponding CERT or the country CERT. Do you also follow the same kind of procedure, and do you report incident to concerned CERTs also? |  | 2019-01-25
2017-10-10 | Denise Michel via email | CZDS | Please provide data on CZDS performance and information on compliance actions regarding CZDS, including Rgy failures to provide daily data, rate limiting, denial of access by Registries, compliance actions/results from actions, pending improvements | Data regarding complaints received by Contractual Compliance regarding zone file access via the Centralized Zone Data Service (CZDS) is available in the Zone File Access complaints portion of the Metrics and Dashboards section (https://features.icann.org/compliance) in Contractual Compliance Performance Measurement & Reporting under the Registry data. There are additional metrics under the Bulk Zone File category of the same section, which relates to a registry operator’s provision of bulk zone file access to ICANN. ICANN provides different levels of reporting: - Monthly Dashboard - for example link to October dashboard (https://features.icann.org/compliance/dashboard/1018/report) - Quarterly Reports - for example link to Jul - Sept Report (https://features.icann.org/compliance/dashboard/report-list) which contains different reports to address this question: - the Registry Complaints per Compliance Approach & Process; - Registry Closed Complaints by Closure Code - Annual Report - summary of volume of complaints across the compliance process within a complaint type. Regarding CZDS complaints - ICANN receives complaints about either lack of registry response to requests or denial/revocation of access. Regarding bulk zone file access to ICANN - ICANN monitors this daily for exceptions. Contractual Compliance action is to follow-up with the registry to facilitate resolution of any issue and where applicable enforce the registry agreement obligations. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | WHOIS | For the new gTLDs and registrars that have the highest inaccuracy rates – what processes do you follow, what actions do you take to address? (See SADAG, DAAR) | Contractual Compliance has a standard Approach and Process (https://www.icann.org/resources/pages/approach-processes-2012-02-25-en) that applies across the registrar, registry and audit program. Contractual Compliance monitors complaints to identify patterns and systemic issues of noncompliance within and across the complaint types and the contracted parties.This effort is useful in identifying trends of issues and most importantly in identifying opportunities to conduct outreach or additional proactive monitoring. For example, based on trends identified by Contractual Compliance (including review of WHOIS inaccuracy complaints submitted by the public and generated as a result of the WHOIS ARS), Contractual Compliance launched a WHOIS Inquiry effort in 2016 that focused on registrars in China and Korea. These inquiries focused on issues with the 2013 RAA WHOIS Accuracy Specification Program (WAPS) requirements. These efforts continued for registrars in China, United States and other regions. Please refer to the annual update published at this link: https://www.icann.org/en/system/files/files/annual-2016-31jan17-en.pdf . Outreach efforts are ongoing; please refer to Outreach page (https://www.icann.org/resources/compliance-reporting-performance) for more information. | 2018-12-14 | 2018-12-11
For example, does Compliance treat registrars with higher accuracy rates to greater scrutiny & compliance activity? If not, why?
2017-10-10 | Denise Michel via email | WHOIS | What trends is Compliance seeing in the Periodic Reporting-- are accuracy rates going up or down? | Contractual Compliance has observed a reduction in WHOIS Inaccuracy complaints being filed over the course of 2018 (https://features.icann.org/compliance/prevention-stats). This could be due to limited access to WHOIS data. The General Data Protection Regulation (GDPR) and the Temporary Specification for gTLD Registration Data has limited the amount of Whois data that is published. Contractual Compliance has adjusted the review of complaints to account for the changes in registration data. For any complaint review that requires unredacted registration data, ICANN requests specific data from contracted party; it is an additional step in the review of the complaint. The Expedited Policy Development Process (EPDP) work that is currently ongoing will be key to future Whois data reviews and analysis. Please note the volume of received complaints only represent the number of complaints that were reported and does not mean that all complaints are valid. For example for the month of October 2018, ICANN received 1255 WHOIS Inaccuracy complaints, closed 962 before sending to the registrar and processed 293. Please refer to the quarterly Registrar Closed Complaints by Closure Code to learn more about the reasons. Generally speaking, most are closed before sending to a registrar for reasons like, duplicate complaint, domain name is suspended already. | 2018-12-14 | 2018-12-11
If the rates are going down-- how does Compliance change its activities to determine the root cause?
2017-10-10 | Denise Michel via email | WHOIS | What contract changes would Compliance like to see to enhance its ability to respond to complaints of inaccurate WHOIS? | Contractual Compliance does not see a need to change the Registrar Accreditation Agreement to respond to complaints of inaccurate WHOIS. Additionally, the Registration Data Access Protocol (https://www.icann.org/rdap) work is underway and should address among other things, standardization, access and security. Contractual Compliance will respond to any complaints of inaccurate WHOIS according to the then-effective agreements and policies. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | WHOIS | Does ICANN Compliance treat WHOIS complaints differently if the complaint is coupled with allegations of DNS abuse. Why not? | Contractual Compliance reviews all complaints from a holistic perspective to determine whether multiple issues may be in scope of the ICANN agreements and policies and need to be addressed by a contracted party. Where appropriate, the contracted party is requested to address multiple issues in a single compliance ticket, and if not (e.g., where different contractual timelines are applicable to each issue), the issues will be addressed separately. However, the standard Contractual Compliance Approach and Process is applied to all compliance matters regardless of topic. | 2018-12-14 | 2018-12-11
Could ICANN Compliance have a different process for responding to WHOIS complaints when coupled with DNS abuse and cybercrime allegations?
2017-10-10 | Denise Michel via email | WHOIS | How does ICANN Compliance interpret 3.18: Registrar shall take reasonable and prompt steps to investigate and respond appropriately to any reports of abuse. a. What are "reasonable steps" and have there been any instances where Compliance has found that the Registrar did not take reasonable steps? b. Did Compliance seek community input into how to interpret 3.18? c. What changes would Compliance suggest to enhance its ability to take action under 3.18? | Contractual Compliance monitors compliance with Section 3.18 of the 2013 RAA through processing abuse complaints submitted through the Registrar Standards Complaint Form (https://forms.icann.org/en/resources/compliance/complaints/registrars/standards-complaint-form) and by conducting the Registrar Audit Program which includes the obligations of Sections 3.18.1, 3.18.2 and 3.18.3 of the 2013 RAA. For abuse complaints, ICANN collects evidence from the reporter and confirms that the reporter sent abuse report(s) to the registrar’s abuse contact email address before sending the complaint to registrar. Once confirmed, ICANN could request the registrar to provide: 1. A description of the steps taken to investigate and respond to abuse report 2. The amount of time taken to respond to abuse report 3. All correspondence with complainant and registrant 4. The link to website’s abuse contact email and handling procedure 5. The location of dedicated abuse email and telephone for law-enforcement reports 6. The registrar’s WHOIS abuse contacts, email address and phone number 7. Examples of steps registrars have taken to investigate and respond to abuse reports include: 1. Contacting the registrant 2. Requesting and obtaining evidence or licenses 3. Providing hosting provider information to complainant 4. Performing Whois verification 5. Performing transfer upon request of registrant 6. Suspending domain Several blogs have been published on this topic; please refer to the ICANN Contractual Compliance Reports & Blogs page dating back to 2015 (https://www.icann.org/resources/compliance-reporting-performance). For more details on the abuse handling and resolution, please refer to slides 19 - 24 in the Registrar Compliance Program material (https://www.icann.org/resources/pages/registrar-2012-02-25-en). Contractual Compliance does not seek community input into contract interpretation. Contractual Compliance has taken action to enforce Section 3.18. The challenge and delays in enforcing in most cases have been where reporters did not provide sufficient information in their abuse report to the registrar, including information regarding alleged violations of laws/regulations in one or more applicable jurisdictions. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | WHOIS | Is Compliance auditing the requirement under the RAA to: Validate that all postal address fields are consistent across fields (for example: street exists in city, city exists in state/province, city matches postal code) where such information is technically and commercially feasible for the applicable country or territory. | Cross-validation is not included in the scope of an audit because it is not an effective provision per Section 6 of the Transition Addendum to Registrar Accreditation Agreement in the 2013 RAA. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | WHOIS | Is ICANN Compliance auditing the escrow deposits to confirm that the submission matches the total registrations of that registrar, and spot checking for accuracy or that it matches what appears in WHOIS | Contractual Compliance conducts proactive monitoring of registrar data escrow deposits. At ICANN’s request, data escrow agents conduct manual reviews of escrow deposits when a registrar receives a 3rd or Escalated Notice (i.e., there is a potential for breach/termination that requires bulk transfer of domains). Manual reviews include comparing deposited domain registration data with publicly available WHOIS information, ensuring that they match. Contractual Compliance compares the number of domains escrowed with the number of domains under the registrar’s management, as reported by registry operators. In cases where the numbers are different, ICANN will send inquiries to registrars seeking additional information regarding the discrepancy. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | WHOIS | Has ICANN Compliance considered having an "emergency response" submission for egregious instances of DNS Abuse? | No. The ICANN agreements and policies as currently defined do not authorize ICANN to require registries or registrars to take a specific action in response to DNS abuse (e.g., suspend or delete potentially abusive domain names), let alone on an expedited basis. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | WHOIS | Is ICANN experiencing "rate limiting" in accessing WHOIS for either compliance purposes or for the WHOIS ARS? | In situations where “rate limiting” occurs, Contractual Compliance works with the registrars to allow ICANN access to the WHOIS data. Restricted access to WHOIS limits Contractual Compliance’s ability to perform its function. For example in complaint types like Domain Renewals and Transfers where a registrant is affected, Contractual Compliance may not be able to confirm the identity of the registrant when processing complaints. As explained in the response to questions #3 and #4 above (3. What trends is Compliance seeing in the Periodic Reporting-- are accuracy rates going up or down? 4. If the rates are going down-- how does Compliance change its activities to determine the root cause?), Contractual Compliance has adjusted the review of complaints to account for the changes in registration data and is requesting the specific data to address issues, where necessary. | 2018-12-14 | 2018-12-11
Does ICANN need unrestricted access to WHOIS to be able to do its compliance activities, WHOIS lookups, and WHOIS ARS?
2017-10-10 | Denise Michel via email | WHOIS | Does ICANN audit the SLAs for WHOIS availability? How often? | The Contractual Compliance audit plan does include a test for registry and registrar WHOIS unavailability. The frequency of an audit of a contracted party varies based on the systemic issues and the audit scope and criteria. Additionally, Contractual Compliance routinely monitors and sends compliance notices to registrars with WHOIS service unavailability. ICANN org also routinely monitors registry operator WHOIS service availability under the requirements of the registry agreement and failures meeting certain defined thresholds will trigger an automated compliance notice. | 2018-12-14 | 2018-12-11
2017-10-10 | Denise Michel via email | WHOIS | Which entities can submit bulk WHOIS compliance complaints? Please explain the requirements/restrictions involved in being able to submit bulk complaints. | Anyone interested in the bulk WHOIS submission can submit a request to be a bulk submitter. To inquire about access to the bulk Whois inaccuracy complaint tool, please email compliance@icann.org with subject: Inquiry about Whois Bulk Submission. Detailed instructions will be provided to the requester. Testing ensures the requester’s bulk submission files meet the required format. In addition, requestors are presented with a terms of use document that they have to review and agree to before they are able to submit any complaints. | 2018-12-14 | 2018-12-11
v