## Slide 1: PDP / EPDP Process Flow and Dependencies https://gnso.icann.org/sites/default/files/file/field-file-attach/annex-2-pdp-manual-30jan18-en.pdf https://gnso.icann.org/sites/default/files/file/field-file-attach/annex-4-epdp-manual-30jan18-en.pdf
Does not apply if already drafted & approved in previous steps
Plan for PDP Initiation
(Staff & Council)
Request an Issue Report
(Board OR Council)
Develop Charter -if not already done-
(Drafting Team)
Create Preliminary Issue Report, may include Draft Charter
(Staff)
Public Comment (Community)
Create Final Issue Report, includes Comment Analysis
(Staff)
Initiate PDP?
(Council)
Approve Charter?
(Council)
Plan for EPDP Initiation
(Staff & Council)
Develop Charter -if not already done-
(Drafting Team)
Create Scoping Document, includes Team Charter
(Staff & Council)
Initiate EPDP?
(Council)
Approve Charter?
(Council)
Page 1
Reject
Reject
Min 30d
X
X
X
Shorter due to Focus?

## Slide 2
Formation of PDP Team*
(Council)
Board Paper (Staff)
Initial Report
(PDP Team**)
Early Input (SO/AC/SG/Cs)
Final Report, includes Comment Analysis
(PDP Team**)
Adopt Any or All Recs
(Council)
Board Action
(Board)
Formation of EPDP Team
(Council)
Board Action
(Board)
Page 2
* PDP Team may be WG, Task Force, Committee, or Drafting Team
** Team responsible for content; Staff assists with preparation
*** Public Forum Discussion & GAC Notice may occur here
Early Input (SO/AC/SG/Cs)
Initial Report
(EPDP Team**)
Public Comment (Community)
Public Comment (Community)
Final Report, includes Comment Analysis
(EPDP Team**)
May
Propose Changes
Public Comment*** (Community)
Report to Board (Council)
Public Comment*** (Community)
Report to Board (Council)
Board Paper (Staff)
May
Propose Changes
Adopt Any or All Recs
(Council)
Min 35d vs. Min 21d
May
Iterate
May Iterate
Min 30d
Min 21d
Min 30d
Min 21d
Shorter due to Focus?
Shorter due to Focus?